## Submittal Log
Submittal Name |  | Spec Section Number | Spec Sub Section | No. of Copies | Type Code | Preparation By Company Code | Preparation By Contact Code | Approved by Company Code | Approved by Contact Code | Returned by Company Code | Returned by Contact code | Forwarded to Company Code | Forward to Contact code | Activity Start Date | Delivery Lead Time | Fabrication Lead Time | Float Lead Time | Approval Lead Time | Review Lead Time | Preparation Lead Time | Procurement Flag
Polished Concrete Finishing_Polishing | yes | 033543 | 1.4-B | Polishing Schedule : Submit plan showing polished concrete surfaces and schedule of polishing operations for each area of polished concrete before start of polishing operations. Include locations of all joints, including construction joints. | Schedule | Schedule
Polished Concrete Finishing_Product Requiring Color Selection | yes | 033543 | 1.4-C |  | Sample
Polished Concrete Finishing_Installer_Informational | yes | 033543 | 1.5-A |  | Qualifications
Polished Concrete Finishing_Repair Materials_Informational | yes | 033543 | 1.5-B-1 |  | Certificate
Polished Concrete Finishing_Stain Materials_Informational | yes | 033543 | 1.5-B-2 |  | Certificate
Polished Concrete Finishing_Liquid Floor Treatments_Informational | yes | 033543 | 1.5-B-3 |  | Certificate
Polished Concrete Finishing_Penetrating Stain | yes | 033543 | 2.1-A |  | Product Data
Polished Concrete Finishing_Penetrating Liquid Floor Treatments for Polished Concrete Finish | yes | 033543 | 2.2-A |  | Product Data
Concrete Unit Masonry_Masonry Units | yes | 042200 | 1.5-B-1 |  | Shop Drawings
Concrete Unit Masonry_Reinforcing Steel | yes | 042200 | 1.5-B-2 |  | Shop Drawings
Concrete Unit Masonry_Fabricated Flashing | yes | 042200 | 1.5-B-3 |  | Shop Drawings
Concrete Unit Masonry_Testing Agency_Informational | yes | 042200 | 1.6-A |  | Qualifications
Concrete Unit Masonry_Masonry Units_Informational | yes | 042200 | 1.6-B-1 |  | Certificate
Concrete Unit Masonry_Integral Water Repellant used in CMUs_Informational | yes | 042200 | 1.6-B-2 |  | Certificate
Concrete Unit Masonry_Preblended, Dry Mortar Mixes_Informational | yes | 042200 | 1.6-B-3 |  | Certificate
Concrete Unit Masonry_Grout Mixes_Informational | yes | 042200 | 1.6-B-4 |  | Certificate
Concrete Unit Masonry_Reinforcing Bars_Informational | yes | 042200 | 1.6-B-5 |  | Certificate
Concrete Unit Masonry_Joint Reinforcement_Informational | yes | 042200 | 1.6-B-6 |  | Certificate
Concrete Unit Masonry_Anchors, Ties, and Metal Accessories_Informational | yes | 042200 | 1.6-B-7 |  | Certificate
Concrete Unit Masonry_Mix Designs_Informational | yes | 042200 | 1.6-C |  | Mix Design
Concrete Unit Masonry_Statement of Compressive Strength of Masonry_Informational | yes | 042200 | 1.6-D |  | Report
Concrete Unit Masonry_Cold-Weather and Hot-Weather Procedures_Informational | yes | 042200 | 1.6-E |  | Procedures
Concrete Unit Masonry_Drainage Mat | yes | 042200 | 2.10-A |  | Product Data
Concrete Unit Masonry_Preblended, Dry Mortar Mix | yes | 042200 | 2.11-A |  | Product Data
Concrete Unit Masonry_Mortar for Unit Masonry | yes | 042200 | 2.11-B |  | Product Data
Concrete Unit Masonry_Grout for Unit Masonry | yes | 042200 | 2.11-C |  | Product Data
Concrete Unit Masonry_Portland Cement | yes | 042200 | 2.5-A |  | Product Data
Concrete Unit Masonry_Hydrated Lime | yes | 042200 | 2.5-B |  | Product Data
Concrete Unit Masonry_Portland Cement-Lime Mix | yes | 042200 | 2.5-C |  | Product Data
Concrete Unit Masonry_Masonry Cement | yes | 042200 | 2.5-D |  | Product Data
Concrete Unit Masonry_Aggregate for Mortar | yes | 042200 | 2.5-E |  | Product Data
Concrete Unit Masonry_Aggregate for Grout | yes | 042200 | 2.5-F |  | Product Data
Concrete Unit Masonry_Uncoated Steel Reinforcing Bars | yes | 042200 | 2.6-A |  | Product Data
Concrete Unit Masonry_Masonry-Joint Reinforcement | yes | 042200 | 2.6-B |  | Product Data
Concrete Unit Masonry_Hot-Dip Galvanized, Carbon-Steel Wire | yes | 042200 | 2.7-B-1 |  | Product Data
Concrete Unit Masonry_Galvanized-Steel Sheet | yes | 042200 | 2.7-B-2 |  | Product Data
Concrete Unit Masonry_Steel Sheet, Galvanized After Fabrication | yes | 042200 | 2.7-B-3 |  | Product Data
Concrete Unit Masonry_Steel Plates, Shapes, and Bars | yes | 042200 | 2.7-B-4 |  | Product Data
Concrete Unit Masonry_Partition Top Anchors | yes | 042200 | 2.7-C |  | Product Data
Concrete Unit Masonry_Rigid Anchors | yes | 042200 | 2.7-D |  | Product Data
Concrete Unit Masonry_Metal Flashing | yes | 042200 | 2.8-A |  | Product Data
Concrete Unit Masonry_Compressible Filler | yes | 042200 | 2.9-A |  | Product Data
Concrete Unit Masonry_Bond-Breaker Strips | yes | 042200 | 2.9-B |  | Product Data
Cold-Formed Metal Framing_Cold-Formed Steel Framing Materials | yes | 054000 | 1.4-A-1 |  | Product Data
Cold-Formed Metal Framing_Interior Non-Load-Bearing Wall Framing | yes | 054000 | 1.4-A-2 |  | Product Data
Cold-Formed Metal Framing_Vertical Deflection Clips | yes | 054000 | 1.4-A-3 |  | Product Data
Cold-Formed Metal Framing_Single Deflection Track | yes | 054000 | 1.4-A-4 |  | Product Data
Cold-Formed Metal Framing_Drift Clips | yes | 054000 | 1.4-A-5 |  | Product Data
Cold-Formed Metal Framing_Soffit Framing | yes | 054000 | 1.4-A-6 |  | Product Data
Cold-Formed Metal Framing_Power-Actuated Anchors | yes | 054000 | 1.4-A-7 |  | Product Data
Cold-Formed Metal Framing_Cold-Formed Metal Framing | yes | 054000 | 1.4-B |  | Shop Drawings
Cold-Formed Metal Framing_Delegated-Design Submittal | yes | 054000 | 1.4-C |  | Report
Cold-Formed Metal Framing_Testing Agency_Informational | yes | 054000 | 1.5-A |  | Qualifications
Cold-Formed Metal Framing_Welding Certificates_Informational | yes | 054000 | 1.5-B |  | Certificate
Cold-Formed Metal Framing_Studs and Tracks_Informational | yes | 054000 | 1.5-C |  | Certificate
Cold-Formed Metal Framing_Power-Actuated Anchors_Informational | yes | 054000 | 1.5-D-1 |  | Report
Cold-Formed Metal Framing_Mechanical Fasteners_Informational | yes | 054000 | 1.5-D-2 |  | Report
Cold-Formed Metal Framing_Vertical Deflection Clips_Informational | yes | 054000 | 1.5-D-3 |  | Report
Cold-Formed Metal Framing_Horizontal Drift Deflection Clips_Informational | yes | 054000 | 1.5-D-4 |  | Report
Cold-Formed Metal Framing_Miscellaneous Structural Clips and Accessories_Informational | yes | 054000 | 1.5-D-5 |  | Report
Cold-Formed Metal Framing_Nonstandard Cold-Formed Steel Framing Power-Actuated Fasteners_Informational | yes | 054000 | 1.5-E-1 |  | Report
Cold-Formed Metal Framing_Sill Sealer Gasket/Termite Barrier_Informational | yes | 054000 | 1.5-E-2 |  | Report
Cold-Formed Metal Framing_Galvanizing Repair Paint | yes | 054000 | 2.7-A |  | Product Data
Cold-Formed Metal Framing_Cement Grout | yes | 054000 | 2.7-B |  | Product Data
Cold-Formed Metal Framing_Nonmetallic, Nonshrink Grout | yes | 054000 | 2.7-C |  | Product Data
Cold-Formed Metal Framing_Shims | yes | 054000 | 2.7-D |  | Product Data
Cold-Formed Metal Framing_Sill Sealer Gasket | yes | 054000 | 2.7-E |  | Product Data
Metal Fabrications_Nonslip Aggregates and Nonslip-Aggregate Surface Finishes | yes | 055000 | 1.4-A-1 |  | Product Data
Metal Fabrications_Fasteners | yes | 055000 | 1.4-A-2 |  | Product Data
Metal Fabrications_Shop Primers | yes | 055000 | 1.4-A-3 |  | Product Data
Metal Fabrications_Shrinkage-Resisting Grout | yes | 055000 | 1.4-A-4 |  | Product Data
Metal Fabrications_Prefabricated Building Columns | yes | 055000 | 1.4-A-5 |  | Product Data
Metal Fabrications_Slotted Channel Framing | yes | 055000 | 1.4-A-6 |  | Product Data
Metal Fabrications_Alternating Tread Devices | yes | 055000 | 1.4-A-7 |  | Product Data
Metal Fabrications_Metal Bollards | yes | 055000 | 1.4-A-8 |  | Product Data
Metal Fabrications_Abrasive Metal Nosings | yes | 055000 | 1.4-A-9 |  | Product Data
Metal Fabrications_Steel Framing and Supports for Ceiling-Hung Toilet Compartments | yes | 055000 | 1.4-B-1 |  | Shop Drawings
Metal Fabrications_Alternating Tread Devices | yes | 055000 | 1.4-B-10 |  | Shop Drawings
Metal Fabrications_Metal Floor Plate and Supports | yes | 055000 | 1.4-B-11 |  | Shop Drawings
Metal Fabrications_Elevator Pit Sump Covers | yes | 055000 | 1.4-B-12 |  | Shop Drawings
Metal Fabrications_Miscellaneous Steel Trim Including Steel Angle Corner Guards and Loading-Dock Edge Angles | yes | 055000 | 1.4-B-13 |  | Shop Drawings
Metal Fabrications_Metal Bollards | yes | 055000 | 1.4-B-14 |  | Shop Drawings
Metal Fabrications_Abrasive Metal Nosings | yes | 055000 | 1.4-B-15 |  | Shop Drawings
Metal Fabrications_Steel Framing and Supports for Operable Partitions | yes | 055000 | 1.4-B-2 |  | Shop Drawings
Metal Fabrications_Steel Framing and Supports for Overhead Doors | yes | 055000 | 1.4-B-3 |  | Shop Drawings
Metal Fabrications_Steel Framing and Supports for Countertops | yes | 055000 | 1.4-B-4 |  | Shop Drawings
Metal Fabrications_Steel Framing and Supports for Laboratory Equipment | yes | 055000 | 1.4-B-5 |  | Shop Drawings
Metal Fabrications_Elevator Machine Beams, Hoist Beams and Divider Beams | yes | 055000 | 1.4-B-6 |  | Shop Drawings
Metal Fabrications_Steel Shapes for Supporting Elevator Door Sills | yes | 055000 | 1.4-B-7 |  | Shop Drawings
Metal Fabrications_Prefabricated Building Columns | yes | 055000 | 1.4-B-8 |  | Shop Drawings
Metal Fabrications_Shelf Angles | yes | 055000 | 1.4-B-9 |  | Shop Drawings
Metal Fabrications_Extruded Nosing | yes | 055000 | 1.4-C |  | Sample
Metal Fabrications_Delegated-Design Submittal | yes | 055000 | 1.4-D |  | Report
Metal Fabrications_Professional Engineer_Informational | yes | 055000 | 1.5-A |  | Qualifications
Metal Fabrications_Mill Certificates_Informational | yes | 055000 | 1.5-B |  | Certificate
Metal Fabrications_Welding Certificates_Informational | yes | 055000 | 1.5-C |  | Certificate
Metal Fabrications_Paint Compatibility Certificates_Informational | yes | 055000 | 1.5-D |  | Certificate
Metal Fabrications_Research Reports Post-Installed Anchors_Informational | yes | 055000 | 1.5-E |  | Report
Metal Grating Stairs_Gratings | yes | 055119 | 1.4-A-1 |  | Product Data
Metal Grating Stairs_Shop Primer Products | yes | 055119 | 1.4-A-2 |  | Product Data
Metal Grating Stairs_Grout | yes | 055119 | 1.4-A-3 |  | Product Data
Metal Grating Stairs_Metal Grating Stairs | yes | 055119 | 1.4-B |  | Shop Drawings
Metal Grating Stairs_Delegated-Design Submittal | yes | 055119 | 1.4-C |  | Report
Metal Grating Stairs_Professional Engineer_Informational | yes | 055119 | 1.5-A |  | Qualifications
Metal Grating Stairs_Welding Certificates_Informational | yes | 055119 | 1.5-B |  | Certificate
Metal Grating Stairs_Paint Compatibility Certificates_Informational | yes | 055119 | 1.5-C |  | Certificate
Metal Grating Stairs_Metal Surfaces | yes | 055119 | 2.2-A |  | Product Data
Metal Grating Stairs_Steel Plates, Shapes, and Bars | yes | 055119 | 2.2-B |  | Product Data
Metal Grating Stairs_Rolled-Steel Floor Plate | yes | 055119 | 2.2-C |  | Product Data
Metal Grating Stairs_Steel Bars for Grating Treads | yes | 055119 | 2.2-D |  | Product Data
Metal Grating Stairs_Steel Wire Rod for Grating Crossbars | yes | 055119 | 2.2-E |  | Product Data
Metal Grating Stairs_Aluminum Bars for Grating Treads | yes | 055119 | 2.2-F |  | Product Data
Metal Grating Stairs_Woven-Wire Mesh | yes | 055119 | 2.2-H |  | Product Data
Metal Grating Stairs_Bolts and Nuts | yes | 055119 | 2.3-B |  | Product Data
Metal Grating Stairs_Anchor Bolts | yes | 055119 | 2.3-C |  | Product Data
Metal Grating Stairs_Post-Installed Anchors | yes | 055119 | 2.3-D |  | Product Data
Metal Grating Stairs_Welding Electrodes | yes | 055119 | 2.4-A |  | Product Data
Metal Grating Stairs_Shop Primers | yes | 055119 | 2.4-B |  | Product Data
Metal Grating Stairs_Universal Shop Primer | yes | 055119 | 2.4-C |  | Product Data
Metal Grating Stairs_Zinc-Rich Primer | yes | 055119 | 2.4-D |  | Product Data
Metal Grating Stairs_Shop Primer for Galvanized Steel | yes | 055119 | 2.4-E |  | Product Data
Metal Grating Stairs_Galvanizing Repair Paint | yes | 055119 | 2.4-F |  | Product Data
Metal Grating Stairs_Nonmetallic, Shrinkage-Resistant Grout | yes | 055119 | 2.4-G |  | Product Data
Pipe and Tube Railings_Manufacturer's Product Lines of Mechanically Connected Railings | yes | 055213 | 1.4-A-1 |  | Product Data
Pipe and Tube Railings_Fasteners | yes | 055213 | 1.4-A-2 |  | Product Data
Pipe and Tube Railings_Post-Installed Anchors | yes | 055213 | 1.4-A-3 |  | Product Data
Pipe and Tube Railings_Handrail Brackets | yes | 055213 | 1.4-A-4 |  | Product Data
Pipe and Tube Railings_Shop Primer | yes | 055213 | 1.4-A-5 |  | Product Data
Pipe and Tube Railings_Intermediate Coats and Topcoats | yes | 055213 | 1.4-A-6 |  | Product Data
Pipe and Tube Railings_Nonshrink, Nonmetallic Grout | yes | 055213 | 1.4-A-7 |  | Product Data
Pipe and Tube Railings_Anchoring Cement | yes | 055213 | 1.4-A-8 |  | Product Data
Pipe and Tube Railings_Metal Finishes | yes | 055213 | 1.4-A-9 |  | Product Data
Pipe and Tube Railings_Paint Products | yes | 055213 | 1.4-A-10 |  | Product Data
Pipe and Tube Railings_Pipe and Tube Railings | yes | 055213 | 1.4-B |  | Shop Drawings
Pipe and Tube Railings_Assembled Sample of Railing System | yes | 055213 | 1.4-C |  | Sample
Pipe and Tube Railings_Delegated-Design Submittal | yes | 055213 | 1.4-D |  | Report
Pipe and Tube Railings_Delegated-Design Professional Engineer_Informational | yes | 055213 | 1.5-A |  | Qualifications
Pipe and Tube Railings_Mill Certificates_Informational | yes | 055213 | 1.5-C |  | Certificate
Pipe and Tube Railings_Welding Certificates_Informational | yes | 055213 | 1.5-B |  | Certificate
Pipe and Tube Railings_Paint Compatibility Certificates_Informational | yes | 055213 | 1.5-D |  | Certificate
Pipe and Tube Railings_Product Test Reports_Informational | yes | 055213 | 1.5-E |  | Report
Pipe and Tube Railings_Post-Installed Anchors_Informational | yes | 055213 | 1.5-F |  | Report
Glazed Decorative Metal Railings_Glass Products | yes | 057313 | 1.5-A-1 |  | Product Data
Glazed Decorative Metal Railings_Glazing Cement and Accessories for Structural Glass Railings | yes | 057313 | 1.5-A-2 |  | Product Data
Glazed Decorative Metal Railings_Sealant and Accessories for Structural Glass Railings | yes | 057313 | 1.5-A-3 |  | Product Data
Glazed Decorative Metal Railings_Fasteners | yes | 057313 | 1.5-A-4 |  | Product Data
Glazed Decorative Metal Railings_Nonshrink, Nonmetallic Grout | yes | 057313 | 1.5-A-5 |  | Product Data
Glazed Decorative Metal Railings_Anchoring Cement | yes | 057313 | 1.5-A-6 |  | Product Data
Glazed Decorative Metal Railings_Glazed Decorative Metal Railings | yes | 057313 | 1.5-B |  | Shop Drawings
Glazed Decorative Metal Railings_Assembled Sample Of Railing System | yes | 057313 | 1.5-C |  | Sample
Glazed Decorative Metal Railings_Delegated-Design Submittal | yes | 057313 | 1.5-D |  | Report
Glazed Decorative Metal Railings_Professional Engineer_Informational | yes | 057313 | 1.6-A |  | Qualifications
Glazed Decorative Metal Railings_Mill Certificates_Informational | yes | 057313 | 1.6-B |  | Certificate
Glazed Decorative Metal Railings_Product Test Reports_Informational | yes | 057313 | 1.6-C |  | Report
Glazed Decorative Metal Railings_Glazed Decorative Metal Railings_Informational | yes | 057313 | 1.6-D |  | Report
Glazed Decorative Metal Railings_Preconstruction Test Reports_Informational | yes | 057313 | 1.6-E |  | Report
Glazed Decorative Metal Railings_Handrail Brackets | yes | 057313 | 2.7-A |  | Product Data
Miscellaneous Rough Carpentry_Preservative-Treated Wood_Informational | yes | 061053 | 1.5-A-1 |  | Report
Miscellaneous Rough Carpentry_Fire-Retardant-Treated Wood_Informational | yes | 061053 | 1.5-A-2 |  | Report
Miscellaneous Rough Carpentry_Power-Driven Fasteners_Informational | yes | 061053 | 1.5-A-3 |  | Report
Miscellaneous Rough Carpentry_Post-Installed Anchors_Informational | yes | 061053 | 1.5-A-4 |  | Report
Miscellaneous Rough Carpentry_Metal Framing Anchors_Informational | yes | 061053 | 1.5-A-5 |  | Report
Miscellaneous Rough Carpentry_Lumber | yes | 061053 | 2.1-A |  | Product Data
Miscellaneous Rough Carpentry_Preservative Chemicals | yes | 061053 | 2.2-A-1 |  | Product Data
Miscellaneous Rough Carpentry_Fire-Retardant-Treated Lumber and Plywood By Pressure Process | yes | 061053 | 2.3-B |  | Product Data
Miscellaneous Rough Carpentry_Dimension Lumber Items | yes | 061053 | 2.4-B |  | Product Data
Miscellaneous Rough Carpentry_Equipment Backing Panels | yes | 061053 | 2.5-A |  | Product Data
Miscellaneous Rough Carpentry_Nails, Brads, and Staples | yes | 061053 | 2.6-B |  | Product Data
Miscellaneous Rough Carpentry_Screws for Fastening To Metal Framing | yes | 061053 | 2.6-C |  | Product Data
Miscellaneous Rough Carpentry_Power-Driven Fasteners | yes | 061053 | 2.6-D |  | Product Data
Miscellaneous Rough Carpentry_Post-Installed Anchors | yes | 061053 | 2.6-E |  | Product Data
Miscellaneous Rough Carpentry_Flexible Flashing | yes | 061053 | 2.7-A |  | Product Data
Interior Finish Carpentry_Exposed Product and Color and Texture | yes | 062023 | 1.3-A |  | Sample
Interior Finish Carpentry_Species and Cut of Lumber and Panel | yes | 062023 | 1.3-B |  | Sample
Interior Finish Carpentry_Lumber | yes | 062023 | 2.1-A |  | Product Data
Interior Finish Carpentry_Softwood Plywood | yes | 062023 | 2.1-B |  | Product Data
Interior Finish Carpentry_Hardboard | yes | 062023 | 2.1-C |  | Product Data
Interior Finish Carpentry_Moldings for Opaque Finish (Painted Finish) | yes | 062023 | 2.2-A |  | Product Data
Interior Finish Carpentry_Closet Shelving | yes | 062023 | 2.3-A |  | Product Data
Interior Finish Carpentry_Shelf Cleats | yes | 062023 | 2.3-B |  | Product Data
Interior Finish Carpentry_Shelf Brackets with Rod Support | yes | 062023 | 2.3-C |  | Product Data
Interior Finish Carpentry_Wood Clothes Rods | yes | 062023 | 2.3-D |  | Product Data
Interior Finish Carpentry_Fasteners for Interior Finish Carpentry | yes | 062023 | 2.4-A |  | Product Data
Wood-Veneer-Faced Architectural Cabinets_Architectural Cabinets | yes | 064113 | 1.5-B |  | Shop Drawings
Wood-Veneer-Faced Architectural Cabinets_Exposed Finish | yes | 064113 | 1.5-C |  | Sample
Wood-Veneer-Faced Architectural Cabinets_Veneer Leaves | yes | 064113 | 1.5-D-1 |  | Sample
Wood-Veneer-Faced Architectural Cabinets_Lumber and Panel Products with Shop-Applied Opaque Finish | yes | 064113 | 1.5-D-2 |  | Sample
Wood-Veneer-Faced Architectural Cabinets_Corner Pieces | yes | 064113 | 1.5-D-3 |  | Sample
Wood-Veneer-Faced Architectural Cabinets_Exposed Cabinet Hardware and Accessories | yes | 064113 | 1.5-D-4 |  | Sample
Wood-Veneer-Faced Architectural Cabinets_Manufacturer and Installer_Informational | yes | 064113 | 1.6-A |  | Qualifications
Wood-Veneer-Faced Architectural Cabinets_Product Certificates_Informational | yes | 064113 | 1.6-B |  | Certificate
Wood-Veneer-Faced Architectural Cabinets_Fire-Retardant-Treated Materials, From ICC-ES_Informational | yes | 064113 | 1.6-C |  | Report
Wood-Veneer-Faced Architectural Cabinets_Field Quality-Control Reports_Informational | yes | 064113 | 1.6-D |  | Report
Wood-Veneer-Faced Architectural Cabinets_Wood Cabinets for Transparent Finish | yes | 064113 | 2.3 |  | Product Data
Wood-Veneer-Faced Architectural Cabinets_Wood Products | yes | 064113 | 2.4-A |  | Product Data
Wood-Veneer-Faced Architectural Cabinets_Composite Wood Products | yes | 064113 | 2.4-B |  | Product Data
Wood-Veneer-Faced Architectural Cabinets_Fire-Retardant-Treated Materials | yes | 064113 | 2.5-A |  | Product Data
Wood-Veneer-Faced Architectural Cabinets_Fire-Retardant-Treated Lumber and Plywood | yes | 064113 | 2.5-B |  | Product Data
Wood-Veneer-Faced Architectural Cabinets_Fire-Retardant Particleboard | yes | 064113 | 2.5-C |  | Product Data
Wood-Veneer-Faced Architectural Cabinets_Fire-Retardant Fiberboard | yes | 064113 | 2.5-D |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Plastic-Laminate-Clad Architectural Cabinetss | yes | 064116 | 1.4-B |  | Shop Drawings
Plastic-Laminate-Clad Architectural Cabinets_Plastic Laminates | yes | 064116 | 1.4-C-1 |  | Sample
Plastic-Laminate-Clad Architectural Cabinets_Corner Pieces | yes | 064116 | 1.4-C-2 |  | Sample
Plastic-Laminate-Clad Architectural Cabinets_Exposed Cabinets Hardware and Accessories | yes | 064116 | 1.4-C-3 |  | Sample
Plastic-Laminate-Clad Architectural Cabinets_Manufacturer and Installer_Informational | yes | 064116 | 1.5-A |  | Qualifications
Plastic-Laminate-Clad Architectural Cabinets_Composite Wood Products_Informational | yes | 064116 | 1.5-B-1 |  | Certificate
Plastic-Laminate-Clad Architectural Cabinets_Adhesives_Informational | yes | 064116 | 1.5-B-2 |  | Certificate
Plastic-Laminate-Clad Architectural Cabinets_Fire-Retardant-Treated Materials, From ICC-ES_Informational | yes | 064116 | 1.5-C |  | Report
Plastic-Laminate-Clad Architectural Cabinets_Field Quality-Control Reports_Informational | yes | 064116 | 1.5-D |  | Report
Plastic-Laminate-Clad Architectural Cabinets_Plastic-Laminate-Clad Architectural Cabinetss | yes | 064116 | 2.1 |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Wood Products | yes | 064116 | 2.2-A |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Composite Wood Products | yes | 064116 | 2.2-B |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Fire-Retardant-Treated Materials | yes | 064116 | 2.3-A |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Fire-Retardant-Treated Lumber and Plywood | yes | 064116 | 2.3-B |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Fire-Retardant Particleboard | yes | 064116 | 2.3-C |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Fire-Retardant Fiberboard | yes | 064116 | 2.3-D |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Butt Hinges | yes | 064116 | 2.4-A |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Frameless Concealed Hinges (European Type) | yes | 064116 | 2.4-B |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Back-Mounted Pulls | yes | 064116 | 2.4-C |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Wire Pulls | yes | 064116 | 2.4-D |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Catches | yes | 064116 | 2.4-E |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Adjustable Shelf Standards and Supports | yes | 064116 | 2.4-F |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Shelf Rests | yes | 064116 | 2.4-G |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Drawer Slides | yes | 064116 | 2.4-H |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Slides for Sliding Glass Doors | yes | 064116 | 2.4-I |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Door Locks | yes | 064116 | 2.4-J |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Drawer Locks | yes | 064116 | 2.4-K |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Door and Drawer Silencers | yes | 064116 | 2.4-L |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Exposed Hardware Finishes | yes | 064116 | 2.4-M |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Furring, Blocking, Shims, and Hanging Strips | yes | 064116 | 2.5-A |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Anchors | yes | 064116 | 2.5-B |  | Product Data
Plastic-Laminate-Clad Architectural Cabinets_Adhesive for Bonding Plastic Laminate | yes | 064116 | 2.5-C |  | Product Data
Preparation for Reroofing_Temporary Roofing Submittal | yes | 070150.19 | 1.6-B |  | Product Data
Preparation for Reroofing_Installer | yes | 070150.19 | 1.7-A |  | Qualifications
Preparation for Reroofing_Fastener Pull-Out Test Report | yes | 070150.19 | 1.7-B |  | Report
Preparation for Reroofing_Photographs Or Videotape | yes | 070150.19 | 1.7-C |  | Report
Preparation for Reroofing_Landfill Records | yes | 070150.19 | 1.7-D |  | Record Drawing
Preparation for Reroofing_EPS Insulation | yes | 070150.19 | 2.1-A |  | Product Data
Preparation for Reroofing_Plywood | yes | 070150.19 | 2.1-B |  | Product Data
Preparation for Reroofing_OSB | yes | 070150.19 | 2.1-C |  | Product Data
Preparation for Reroofing_Sheathing Paper | yes | 070150.19 | 2.2-B |  | Product Data
Preparation for Reroofing_Base Sheet | Yes | 070150.19 | 2.2-C |  | Product Data
Preparation for Reroofing_Glass-Fiber Felts | Yes | 070150.19 | 2.2-D |  | Product Data
Preparation for Reroofing_Asphalt Primer | Yes | 070150.19 | 2.2-E |  | Product Data
Preparation for Reroofing_Roofing Asphalt | Yes | 070150.19 | 2.2-F |  | Product Data
Preparation for Reroofing_Base Sheet Fasteners | Yes | 070150.19 | 2.2-G |  | Product Data
Preparation for Reroofing_Fasteners | Yes | 070150.19 | 2.3-D |  | Product Data
Preparation for Reroofing_Auxiliary Reroofing Materials | Yes | 070150.19 | 2.4 |  | Product Data
Crystalline Waterproofing_Applicator_Informational | Yes | 071616 | 1.5-A |  | Qualifications
Crystalline Waterproofing_Waterproofing, Patching, and Plugging Material_Informational | Yes | 071616 | 1.5-B |  | Certificate
Crystalline Waterproofing_Product Test Reports_Informational | Yes | 071616 | 1.5-C |  | Report
Crystalline Waterproofing_Field Quality-Control Reports_Informational | Yes | 071616 | 1.5-D |  | Report
Crystalline Waterproofing_Crystalline Waterproofing | Yes | 071616 | 2.1-A |  | Product Data
Crystalline Waterproofing_Patching Compound | Yes | 071616 | 2.2-A |  | Product Data
Crystalline Waterproofing_Plugging Compound | Yes | 071616 | 2.2-B |  | Product Data
Crystalline Waterproofing_Crystalline Waterproofing | Yes | 071616 | 2.3-A |  | Mix Design
Thermal Insulation_Polyisocyanurate Foam-Plastic Board Insulation | Yes | 072100 | 1.3-A-1 |  | Product Data
Thermal Insulation_Glass-Fiber Blanket Insulation | Yes | 072100 | 1.3-A-2 |  | Product Data
Thermal Insulation_Mineral-Wool Blanket Insulation | Yes | 072100 | 1.3-A-3 |  | Product Data
Thermal Insulation_Installer's Certification_Informational | Yes | 072100 | 1.4-A |  | Certificate
Thermal Insulation_Product Test Reports_Informational | Yes | 072100 | 1.4-B |  | Report
Thermal Insulation_Foam-Plastic Insulation_Informational | Yes | 072100 | 1.4-C |  | Report
Thermal Insulation_Polyisocyanurate Board Insulation, Glass-Fiber-Mat Faced | Yes | 072100 | 2.1-A |  | Product Data
Thermal Insulation_Glass-Fiber Blanket Insulation, Unfaced | Yes | 072100 | 2.2-A |  | Product Data
Thermal Insulation_Glass-Fiber Blanket Insulation, Polypropylene-Scrim-Kraft Faced | Yes | 072100 | 2.2-B |  | Product Data
Thermal Insulation_Mineral-Wool Blanket Insulation, Unfaced | Yes | 072100 | 2.3-A |  | Product Data
Thermal Insulation_Mineral-Wool Blanket Insulation, Reinforced-Foil Faced | Yes | 072100 | 2.3-B |  | Product Data
Thermal Insulation_Adhesively Attached, Spindle-Type Anchors | Yes | 072100 | 2.4-A |  | Product Data
Thermal Insulation_Adhesively Attached, Angle-Shaped, Spindle-Type Anchors | Yes | 072100 | 2.4-B |  | Product Data
Thermal Insulation_Insulation-Retaining Washers | Yes | 072100 | 2.4-C |  | Product Data
Thermal Insulation_Insulation Standoff | Yes | 072100 | 2.4-D |  | Product Data
Thermal Insulation_Anchor Adhesive | Yes | 072100 | 2.4-E |  | Product Data
Thermal Insulation_Glass-Fiber Insulation | Yes | 072100 | 2.5-A-1 |  | Product Data
Thermal Insulation_Spray Polyurethane Foam Insulation | Yes | 072100 | 2.5-A-2 |  | Product Data
Thermal Insulation_Adhesive for Bonding Insulation | Yes | 072100 | 2.5-B |  | Product Data
Fluid-Applied Membrane Air Barriers_Air-Barrier Assemblies | Yes | 072726 | 1.5-B |  | Shop Drawings
Fluid-Applied Membrane Air Barriers_Installer_Informational | Yes | 072726 | 1.6-A |  | Qualifications
Fluid-Applied Membrane Air Barriers_Product Certificates_Informational | Yes | 072726 | 1.6-B |  | Certificate
Fluid-Applied Membrane Air Barriers_Product Test Reports_Informational | Yes | 072726 | 1.6-C |  | Report
Fluid-Applied Membrane Air Barriers_Field Quality-Control Reports_Informational | Yes | 072726 | 1.6-D |  | Report
Fluid-Applied Membrane Air Barriers_High-Build, Vapor-Permeable Air Barrier | Yes | 072726 | 2.3-A |  | Product Data
Fluid-Applied Membrane Air Barriers_Primer | Yes | 072726 | 2.4-B |  | Product Data
Fluid-Applied Membrane Air Barriers_Stainless-Steel Sheet | Yes | 072726 | 2.4-C |  | Product Data
Fluid-Applied Membrane Air Barriers_Preformed Silicone Extrusion | Yes | 072726 | 2.4-D |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Insulation and Roof System Component Fasteners | Yes | 075423 | 1.5-A |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Thermoplastic-Polyolefin (TPO) Roofing | Yes | 075423 | 1.5-B |  | Shop Drawings
Thermoplastic-Polyolefin (TPO) Roofing_Roof Membrane and Flashings | Yes | 075423 | 1.5-C-1 |  | Sample
Thermoplastic-Polyolefin (TPO) Roofing_Walkway Pads or Rolls | Yes | 075423 | 1.5-C-2 |  | Sample
Thermoplastic-Polyolefin (TPO) Roofing_Wind Uplift Resistance Submittal for Roofing System | Yes | 075423 | 1.5-D |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Installer, Manufacturer and Testing Agency_Informational | Yes | 075423 | 1.6-A |  | Qualifications
Thermoplastic-Polyolefin (TPO) Roofing_Performance Requirement Certificate_Informational | Yes | 075423 | 1.6-B-1 |  | Certificate
Thermoplastic-Polyolefin (TPO) Roofing_Special Warranty Certificate_Informational | Yes | 075423 | 1.6-B-2 |  | Certificate
Thermoplastic-Polyolefin (TPO) Roofing_Roof Membrane and Insulation_Informational | Yes | 075423 | 1.6-C |  | Test Data
Thermoplastic-Polyolefin (TPO) Roofing_Components of Roofing System_Informational | Yes | 075423 | 1.6-D |  | Report
Thermoplastic-Polyolefin (TPO) Roofing_Concrete Internal Relative Humidity Test Reports_Informational | Yes | 075423 | 1.6-E-1 |  | Test Data
Thermoplastic-Polyolefin (TPO) Roofing_Fastener-Pullout Test Results and Manufacturer'S Revised Requirements for Fastener Patterns_Informational | Yes | 075423 | 1.6-E-2 |  | Test Data
Thermoplastic-Polyolefin (TPO) Roofing_Field Quality-Control Reports_Informational | Yes | 075423 | 1.6-F |  | Report
Thermoplastic-Polyolefin (TPO) Roofing_Manufacturer'S Special Warranties_Informational | Yes | 075423 | 1.6-G |  | Sample
Thermoplastic-Polyolefin (TPO) Roofing_Thermoplastic Polyolefin (TPO) Roofing | Yes | 075423 | 2.2 |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Sheet Flashing | Yes | 075423 | 2.3-B |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Prefabricated Pipe Flashings | Yes | 075423 | 2.3-C |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Roof Vents | Yes | 075423 | 2.3-D |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Bonding Adhesive | Yes | 075423 | 2.3-E |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Slip Sheet | Yes | 075423 | 2.3-F |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Metal Termination Bars | Yes | 075423 | 2.3-G |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Metal Battens | Yes | 075423 | 2.3-H |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Fasteners | Yes | 075423 | 2.3-I |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Miscellaneous Accessories | Yes | 075423 | 2.3-J |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Substrate Boards | Yes | 075423 | 2.4 |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Polyethylene Film | Yes | 075423 | 2.5-A |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Self-Adhering-Sheet Vapor Retarder | Yes | 075423 | 2.5-B |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Glass-Fiber Felts | Yes | 075423 | 2.5-C |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Polyisocyanurate Board Insulation | Yes | 075423 | 2.6-B |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Tapered Insulation | Yes | 075423 | 2.6-C |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Cover Board | Yes | 075423 | 2.7-C |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Protection Mat | Yes | 075423 | 2.7-D |  | Product Data
Thermoplastic-Polyolefin (TPO) Roofing_Flexible Walkways | Yes | 075423 | 2.8-A |  | Product Data
Roof Accessories_Roof Accessories | Yes | 077200 | 1.4-B |  | Shop Drawings
Roof Accessories_Each Exposed Product and for Each Color and Texture Specified | Yes | 077200 | 1.4-C |  | Sample
Roof Accessories_Delegatd Design Roof Curbs, Equipment Supports | Yes | 077200 | 1.4-D |  | Report
Roof Accessories_Coordination Drawings_Informational | Yes | 077200 | 1.5-A |  | Record Drawing
Roof Accessories_Sample Warranties_Informational | Yes | 077200 | 1.5-B |  | Sample
Roof Accessories_Roof Curbs | Yes | 077200 | 2.2 |  | Product Data
Roof Accessories_Equipment Supports | Yes | 077200 | 2.3 |  | Product Data
Roof Accessories_Roof Hatches | Yes | 077200 | 2.4 |  | Product Data
Roof Accessories_Fixed-Height Cradle-Type Pipe Supports | Yes | 077200 | 2.5-A |  | Product Data
Roof Accessories_Adjustable-Height Roller-Bearing Pipe Supports | Yes | 077200 | 2.5-B |  | Product Data
Roof Accessories_Duct Supports | Yes | 077200 | 2.5-C |  | Product Data
Roof Accessories_Exhaust Vent Flashing | Yes | 077200 | 2.6-A |  | Product Data
Roof Accessories_Vent Stack Flashing | Yes | 077200 | 2.6-B |  | Product Data
Roof Accessories_Zinc-Coated (Galvanized) Steel Sheet | Yes | 077200 | 2.7-A |  | Product Data
Roof Accessories_Aluminum-Zinc Alloy-Coated Steel Sheet | Yes | 077200 | 2.7-B |  | Product Data
Roof Accessories_Stainless Steel Sheet and Shapes | Yes | 077200 | 2.7-C |  | Product Data
Roof Accessories_Steel Shapes | Yes | 077200 | 2.7-D |  | Product Data
Roof Accessories_Steel Tube | Yes | 077200 | 2.7-E |  | Product Data
Roof Accessories_Galvanized-Steel Tube | Yes | 077200 | 2.7-F |  | Product Data
Roof Accessories_Steel Pipe | Yes | 077200 | 2.7-G |  | Product Data
Roof Accessories_Cellulosic-Fiber Board Insulation | Yes | 077200 | 2.8-B |  | Product Data
Roof Accessories_Glass-Fiber Board Insulation | Yes | 077200 | 2.8-C |  | Product Data
Roof Accessories_Polyisocyanurate Board Insulation | Yes | 077200 | 2.8-D |  | Product Data
Roof Accessories_Wood Nailers | Yes | 077200 | 2.8-E |  | Product Data
Roof Accessories_Bituminous Coating | Yes | 077200 | 2.8-F |  | Product Data
Roof Accessories_Underlayment | Yes | 077200 | 2.8-G |  | Product Data
Roof Accessories_Fasteners | Yes | 077200 | 2.8-H |  | Product Data
Roof Accessories_Gaskets | Yes | 077200 | 2.8-I |  | Product Data
Roof Accessories_Elastomeric Sealant | Yes | 077200 | 2.8-J |  | Product Data
Applied Fire Protection_Topcoat | Yes | 078100 | 1.5-A-7 |  | Product Data
Applied Fire Protection_Applied Fire Protection | Yes | 078100 | 1.5-B |  | Shop Drawings
Applied Fire Protection_Installer and Testing Agency_Informational | Yes | 078100 | 1.6-A |  | Qualifications
Applied Fire Protection_Each Type of Sprayed Fire-Resistive Material_Informational | Yes | 078100 | 1.6-B |  | Certificate
Applied Fire Protection_Sprayed Fire-Resistive Material_Informational | Yes | 078100 | 1.6-C |  | Report
Applied Fire Protection_Fire Protection_Informational | Yes | 078100 | 1.6-D |  | Report
Applied Fire Protection_Field Quality-Control Reports_Informational | Yes | 078100 | 1.6-E |  | Report
Applied Fire Protection_Sprayed Fire-Resistive Material | Yes | 078100 | 2.2-A |  | Product Data
Applied Fire Protection_Substrate Primers | Yes | 078100 | 2.3-B |  | Product Data
Applied Fire Protection_Bonding Agent | Yes | 078100 | 2.3-C |  | Product Data
Applied Fire Protection_Metal Lath | Yes | 078100 | 2.3-D |  | Product Data
Applied Fire Protection_Reinforcing Fabric | Yes | 078100 | 2.3-E |  | Product Data
Applied Fire Protection_Sealer | Yes | 078100 | 2.3-F |  | Product Data
Applied Fire Protection_Cement-Based Topcoat | Yes | 078100 | 2.3-G-1 |  | Product Data
Penetration Firestopping_Penetration Firestopping System | Yes | 078413 | 1.6-B |  | Schedule
Penetration Firestopping_Installer_Informational | Yes | 078413 | 1.7-A |  | Qualifications
Penetration Firestopping_Each Penetration Firestopping System_Informational | Yes | 078413 | 1.7-B |  | Test Data
Penetration Firestopping_Penetration Firestopping Systems | Yes | 078413 | 2.2-A |  | Product Data
Penetration Firestopping_Penetrations in Fire-Resistance-Rated Walls | Yes | 078413 | 2.2-B |  | Product Data
Penetration Firestopping_Penetrations in Horizontal Assemblies | Yes | 078413 | 2.2-C |  | Product Data
Penetration Firestopping_Exposed Penetration Firestopping Systems | Yes | 078413 | 2.2-D |  | Product Data
Penetration Firestopping_Manufactured Piping Penetration Firestopping System | Yes | 078413 | 2.2-E |  | Product Data
Penetration Firestopping_Accessories | Yes | 078413 | 2.2-F |  | Product Data
Penetration Firestopping_Cast-in-Place Firestop Devices | Yes | 078413 | 2.3-A |  | Product Data
Penetration Firestopping_Latex Sealants | Yes | 078413 | 2.3-B |  | Product Data
Penetration Firestopping_Firestop Devices | Yes | 078413 | 2.3-C |  | Product Data
Penetration Firestopping_Intumescent Composite Sheets | Yes | 078413 | 2.3-D |  | Product Data
Penetration Firestopping_Intumescent Putties | Yes | 078413 | 2.3-E |  | Product Data
Penetration Firestopping_Mortars | Yes | 078413 | 2.3-F |  | Product Data
Penetration Firestopping_Pillows/Bags | Yes | 078413 | 2.3-G |  | Product Data
Penetration Firestopping_Silicone Foams | Yes | 078413 | 2.3-H |  | Product Data
Penetration Firestopping_Silicone Sealants | Yes | 078413 | 2.3-I |  | Product Data
Joint Firestopping_Each Joint Firestopping System | Yes | 078443 | 1.4-B |  | Schedule
Joint Firestopping_Installer_Informational | Yes | 078443 | 1.5-A |  | Qualifications
Joint Firestopping_Each Joint Firestopping System_Informational | Yes | 078443 | 1.5-B |  | Report
Joint Firestopping_Joint Firestopping Systems | Yes | 078443 | 2.2-A |  | Product Data
Joint Firestopping_Joints in or Between Fire-Resistance-Rated Construction | Yes | 078443 | 2.2-B |  | Product Data
Joint Firestopping_Exposed Joint Firestopping Systems | Yes | 078443 | 2.2-C |  | Product Data
Joint Firestopping_Accessories | Yes | 078443 | 2.2-D |  | Product Data
Joint Sealants_Joint-Sealant | Yes | 079200 | 1.3-B |  | Sample
Joint Sealants_Joint-Sealant Schedule | Yes | 079200 | 1.3-C |  | Schedule
Joint Sealants_Testing Agency_Informational | Yes | 079200 | 1.4-A |  | Qualifications
Joint Sealants_Each Kind of Joint Sealant_Informational | Yes | 079200 | 1.4-B |  | Report
Joint Sealants_Preconstruction Laboratory Test Schedule_Informational | Yes | 079200 | 1.4-C |  | Schedule
Joint Sealants_Preconstruction Laboratory Test Reports_Informational | Yes | 079200 | 1.4-D |  | Report
Joint Sealants_Preconstruction Field-Adhesion-Test Reports_Informational | Yes | 079200 | 1.4-E |  | Report
Joint Sealants_Field-Adhesion-Test Reports_Informational | Yes | 079200 | 1.4-F |  | Report
Joint Sealants_Special Warranties_Informational | Yes | 079200 | 1.4-G |  | Sample
Joint Sealants_Joint Sealants | Yes | 079200 | 2.1 |  | Product Data
Joint Sealants_Silicone Joint Sealants | Yes | 079200 | 2.2 |  | Product Data
Joint Sealants_Polyurethane Sealants | Yes | 079200 | 2.3 |  | Product Data
Joint Sealants_Latex Joint Sealants | Yes | 079200 | 2.4 |  | Product Data
Joint Sealants_Joint-Sealant Backing | Yes | 079200 | 2.5 |  | Product Data
Joint Sealants_Primer | Yes | 079200 | 2.6-A |  | Product Data
Joint Sealants_Cleaners for Nonporous Surfaces | Yes | 079200 | 2.6-B |  | Product Data
Joint Sealants_Masking Tape | Yes | 079200 | 2.6-C |  | Product Data
Interior Expansion Joint Cover Assemblies_Expansion Joint Cover Assembly | Yes | 079513.13 | 1.3-B |  | Shop Drawings
Interior Expansion Joint Cover Assemblies_Expansion Joint Cover Assembly Schedule | Yes | 079513.13 | 1.3-C |  | Schedule
Interior Expansion Joint Cover Assemblies_Fire-Resistance-Rated Expansion Joint Cover Assembly_Informational | Yes | 079513.13 | 1.4-A |  | Report
Interior Expansion Joint Cover Assemblies_Hidden-Sightline Floor Joint Cover | Yes | 079513.13 | 2.3-A |  | Product Data
Interior Expansion Joint Cover Assemblies_Metal-Plate Wall Joint Cover | Yes | 079513.13 | 2.4-A |  | Product Data
Interior Expansion Joint Cover Assemblies_Stainless Steel | Yes | 079513.13 | 2.5-A |  | Product Data
Interior Expansion Joint Cover Assemblies_Nonmetallic, Shrinkage-Resistant Grout | Yes | 079513.13 | 2.5-B |  | Product Data
Interior Expansion Joint Cover Assemblies_Polished Finishes | Yes | 079513.13 | 2.6-B |  | Product Data
Interior Expansion Joint Cover Assemblies_Bright, Cold-Rolled, Unpolished Finish | Yes | 079513.13 | 2.6-C |  | Product Data
Interior Expansion Joint Cover Assemblies_Moisture Barriers | Yes | 079513.13 | 2.7-A |  | Product Data
Interior Expansion Joint Cover Assemblies_Manufacturer's Stainless-Steel Attachment Devices | Yes | 079513.13 | 2.7-B |  | Product Data
Hollow Metal Doors and Frames_Hollow Metal Doors and Frames | Yes | 081113 | 1.6-B |  | Shop Drawings
Hollow Metal Doors and Frames_Hollow-Metal Doors and Frames | Yes | 081113 | 1.6-C |  | Sample
Hollow Metal Doors and Frames_Exposed Finish | Yes | 081113 | 1.6-D-1 |  | Sample
Hollow Metal Doors and Frames_Fabrication | Yes | 081113 | 1.6-D-2 |  | Sample
Hollow Metal Doors and Frames_Product Schedule | Yes | 081113 | 1.6-E |  | Schedule
Hollow Metal Doors and Frames_Door Inspector_Informational | Yes | 081113 | 1.7-A |  | Qualifications
Hollow Metal Doors and Frames_Fire-Rated Hollow-Metal Door and Frame Assembly_Informational | Yes | 081113 | 1.7-B |  | Report
Hollow Metal Doors and Frames_Oversize Construction Certification_Informational | Yes | 081113 | 1.7-C |  | Certificate
Hollow Metal Doors and Frames_Field Quality Control Reports_Informational | Yes | 081113 | 1.7-D |  | Report
Hollow Metal Doors and Frames_Heavy-Duty Doors and Frames | Yes | 081113 | 2.3-B |  | Product Data
Hollow Metal Doors and Frames_Extra-Heavy-Duty Doors and Frames | Yes | 081113 | 2.4-B |  | Product Data
Hollow Metal Doors and Frames_Borrowed Lites | Yes | 081113 | 2.5 |  | Product Data
Hollow Metal Doors and Frames_Hollow-Metal Panels | Yes | 081113 | 2.6 |  | Product Data
Hollow Metal Doors and Frames_Jamb Anchors | Yes | 081113 | 2.7-A |  | Product Data
Hollow Metal Doors and Frames_Floor Anchors | Yes | 081113 | 2.7-B |  | Product Data
Hollow Metal Doors and Frames_Floor Anchors for Concrete Slabs With Underlayment | Yes | 081113 | 2.7-C |  | Product Data
Hollow Metal Doors and Frames_Recycled Content Of Steel Products | Yes | 081113 | 2.8-A |  | Product Data
Hollow Metal Doors and Frames_Cold-Rolled Steel Sheet | Yes | 081113 | 2.8-B |  | Product Data
Hollow Metal Doors and Frames_Hot-Rolled Steel Sheet | Yes | 081113 | 2.8-C |  | Product Data
Hollow Metal Doors and Frames_Metallic-Coated Steel Sheet | Yes | 081113 | 2.8-D |  | Product Data
Hollow Metal Doors and Frames_Inserts, Bolts, and Fasteners | Yes | 081113 | 2.8-E |  | Product Data
Hollow Metal Doors and Frames_Power-Actuated Fasteners in Concrete | Yes | 081113 | 2.8-F |  | Product Data
Hollow Metal Doors and Frames_Mineral-Fiber Insulation | Yes | 081113 | 2.8-G |  | Product Data
Hollow Metal Doors and Frames_Glazing | Yes | 081113 | 2.8-H |  | Product Data
Hollow Metal Doors and Frames_Louvers | Yes | 081113 | 2.11 |  | Product Data
Access Doors and Frames_Access Doors and Frames | Yes | 083113 | 1.4-B |  | Schedule
Access Doors and Frames_Flush Access Doors With Concealed Flanges | Yes | 083113 | 2.2-A |  | Product Data
Access Doors and Frames_Fire-Rated, Flush Access Doors With Concealed Flanges | Yes | 083113 | 2.3-A |  | Product Data
Access Doors and Frames_Steel Plates, Shapes, and Bars | Yes | 083113 | 2.4-A |  | Product Data
Access Doors and Frames_Steel Sheet | Yes | 083113 | 2.4-B |  | Product Data
Access Doors and Frames_Metallic-Coated Steel Sheet | Yes | 083113 | 2.4-C |  | Product Data
Access Doors and Frames_Frame Anchors | Yes | 083113 | 2.4-D |  | Product Data
Access Doors and Frames_Inserts, Bolts, and Anchor Fasteners | Yes | 083113 | 2.4-E |  | Product Data
Overhead Coiling Doors_Installation and for Special Components | Yes | 083323 | 1.3-B |  | Shop Drawings
Overhead Coiling Doors_Samples for Initial Selection | Yes | 083323 | 1.3-C |  | Sample
Overhead Coiling Doors_Installer_Informational | Yes | 083323 | 1.4-A |  | Qualifications
Overhead Coiling Doors_Oversize Construction Certification for Door Assemblies_Informational | Yes | 083323 | 1.4-B |  | Certificate
Overhead Coiling Doors_Sample Warranty_Informational | Yes | 083323 | 1.4-C |  | Warranty
Overhead Coiling Doors_Insulated Service Door | Yes | 083323 | 2.3-A |  | Product Data
Overhead Coiling Doors_Door Curtain Slats | Yes | 083323 | 2.3-G |  | Product Data
Overhead Coiling Doors_Bottom Bar | Yes | 083323 | 2.3-H |  | Product Data
Overhead Coiling Doors_Curtain Jamb Guides | Yes | 083323 | 2.3-I |  | Product Data
Overhead Coiling Doors_Hood | Yes | 083323 | 2.3-J |  | Product Data
Overhead Coiling Doors_Locking Devices | Yes | 083323 | 2.3-K |  | Product Data
Overhead Coiling Doors_Manual Door Operator | Yes | 083323 | 2.3-L |  | Product Data
Overhead Coiling Doors_Electric Door Operator | Yes | 083323 | 2.3-M |  | Product Data
Overhead Coiling Doors_Curtain Accessories | Yes | 083323 | 2.3-N |  | Product Data
Overhead Coiling Doors_Door Finish | Yes | 083323 | 2.3-O |  | Product Data
Overhead Coiling Doors_Electrical Components, Devices, and Accessories | Yes | 083323 | 2.4-A |  | Product Data
Overhead Coiling Doors_Steel Door Curtain Slats | Yes | 083323 | 2.5-A-1 |  | Product Data
Overhead Coiling Doors_Aluminum Door Curtain Slats | Yes | 083323 | 2.5-A-2 |  | Product Data
Overhead Coiling Doors_Vision-Panel Glazing | Yes | 083323 | 2.5-A-3 |  | Product Data
Overhead Coiling Doors_Insulation | Yes | 083323 | 2.5-A-4 |  | Product Data
Overhead Coiling Doors_Metal Interior Curtain-Slat Facing | Yes | 083323 | 2.5-A-5 |  | Product Data
Overhead Coiling Doors_Hoods | Yes | 083323 | 2.6 |  | Product Data
Overhead Coiling Doors_Slide Bolt | Yes | 083323 | 2.7-A |  | Product Data
Overhead Coiling Doors_Locking Device Assembly | Yes | 083323 | 2.7-B |  | Product Data
Overhead Coiling Doors_Safety Interlock Switch | Yes | 083323 | 2.7-C |  | Product Data
Overhead Coiling Doors_Weatherseals for Exterior Doors | Yes | 083323 | 2.8-A |  | Product Data
Overhead Coiling Doors_Automatic-Closing Device | Yes | 083323 | 2.8-B |  | Product Data
Overhead Coiling Doors_Counterbalance Barrel | Yes | 083323 | 2.9-B |  | Product Data
Overhead Coiling Doors_Counterbalance Spring | Yes | 083323 | 2.9-C |  | Product Data
Overhead Coiling Doors_Torsion Rod for Counterbalance Shaft | Yes | 083323 | 2.9-D |  | Product Data
Overhead Coiling Doors_Brackets | Yes | 083323 | 2.9-E |  | Product Data
Overhead Coiling Doors_Chain-Hoist Operator | Yes | 083323 | 2.10-B |  | Product Data
Overhead Coiling Doors_Reversible-Type Motor with Controller | Yes | 083323 | 2.11-D |  | Product Data
Overhead Coiling Doors_Limit Switches | Yes | 083323 | 2.11-E |  | Product Data
Overhead Coiling Doors_Obstruction-Detection Devices | Yes | 083323 | 2.11-F |  | Product Data
Overhead Coiling Doors_Control Station | Yes | 083323 | 2.11-G |  | Product Data
Overhead Coiling Doors_Emergency Manual Operation | Yes | 083323 | 2.11-H |  | Product Data
Overhead Coiling Doors_Emergency Operation Disconnect Device | Yes | 083323 | 2.11-I |  | Product Data
Aluminum-Framed Storefronts_Aluminum-Framed Storefronts | Yes | 084313 | 1.5-B |  | Shop Drawings
Aluminum-Framed Storefronts_Units with Factory-Applied Color Finishes | Yes | 084313 | 1.5-C |  | Sample
Aluminum-Framed Storefronts_Each Type of Exposed Finish | Yes | 084313 | 1.5-D |  | Sample
Aluminum-Framed Storefronts_Each Vertical-To-Horizontal Intersection Of Assemblies | Yes | 084313 | 1.5-E |  | Sample
Aluminum-Framed Storefronts_Delegated Design Aluminum-Framed Storefronts | Yes | 084313 | 1.5-F |  | Report
Aluminum-Framed Storefronts_Preconstruction Laboratory Mockup Testing Submittals_Informational | Yes | 084313 | 1.6-A |  | Test Data
Aluminum-Framed Storefronts_Installer and Field Testing Agency_Informational | Yes | 084313 | 1.6-B-1 |  | Qualifications
Aluminum-Framed Storefronts_Professional Engineer'S Experience With Providing Delegated-Design Engineering Services_Informational | Yes | 084313 | 1.6-B-2 |  | Qualifications
Aluminum-Framed Storefronts_Aluminum-Framed Storefronts, Accessories, and Components_Informational | Yes | 084313 | 1.6-C |  | Certificate
Aluminum-Framed Storefronts_Aluminum-Framed Storefronts_Informational | Yes | 084313 | 1.6-D |  | Test Data
Aluminum-Framed Storefronts_Quality-Control Program_Informational | Yes | 084313 | 1.6-E |  | Report
Aluminum-Framed Storefronts_Source Quality-Control Reports_Informational | Yes | 084313 | 1.6-F |  | Report
Aluminum-Framed Storefronts_Field Quality-Control Reports_Informational | Yes | 084313 | 1.6-G |  | Report
Aluminum-Framed Storefronts_Special Warranties_Informational | Yes | 084313 | 1.6-H |  | Sample
Aluminum-Framed Storefronts_Aluminum-Framed Storefront Systems | Yes | 084313 | 2.3 |  | Product Data
Aluminum-Framed Storefronts_Glazing | Yes | 084313 | 2.4-A |  | Product Data
Aluminum-Framed Storefronts_Glazing Gaskets | Yes | 084313 | 2.4-B |  | Product Data
Aluminum-Framed Storefronts_Glazing Sealants | Yes | 084313 | 2.4-C |  | Product Data
Aluminum-Framed Storefronts_Weatherseal Sealants | Yes | 084313 | 2.4-D |  | Product Data
Aluminum-Framed Storefronts_Sheet and Plate | Yes | 084313 | 2.5-A |  | Product Data
Aluminum-Framed Storefronts_Extruded Bars, Rods, Profiles, and Tubes | Yes | 084313 | 2.5-B |  | Product Data
Aluminum-Framed Storefronts_Extruded Structural Pipe and Tubes | Yes | 084313 | 2.5-C |  | Product Data
Aluminum-Framed Storefronts_Structural Profiles | Yes | 084313 | 2.5-D |  | Product Data
Aluminum-Framed Storefronts_Structural Shapes, Plates, and Bars | Yes | 084313 | 2.5-E-1 |  | Product Data
Aluminum-Framed Storefronts_Cold-Rolled Sheet and Strip | Yes | 084313 | 2.5-E-2 |  | Product Data
Aluminum-Framed Storefronts_Hot-Rolled Sheet and Strip | Yes | 084313 | 2.5-E-3 |  | Product Data
Aluminum-Framed Storefronts_Steel Reinforcement Primer | Yes | 084313 | 2.5-F |  | Product Data
Aluminum-Framed Storefronts_Fasteners and Accessories | Yes | 084313 | 2.6-A |  | Product Data
Aluminum-Framed Storefronts_Anchors | Yes | 084313 | 2.6-B |  | Product Data
Aluminum-Framed Storefronts_Concealed Flashing | Yes | 084313 | 2.6-C |  | Product Data
Aluminum-Framed Storefronts_Rigid PVC Filler | Yes | 084313 | 2.6-D |  | Product Data
Door Hardware_Electrified Door Hardware | Yes | 087100 | 1.6-B |  | Shop Drawings
Door Hardware_Each Exposed Product In Each Finish Specified | Yes | 087100 | 1.6-C |  | Sample
Door Hardware_Each Type of Exposed Finish | Yes | 087100 | 1.6-D |  | Sample
Door Hardware_Each Type of Exposed Product | Yes | 087100 | 1.6-E |  | Sample
Door Hardware_Door Hardware Schedule | Yes | 087100 | 1.6-F |  | Schedule
Door Hardware_Keying Schedule | Yes | 087100 | 1.6-G |  | Schedule
Door Hardware_Installer and Architectural Hardware Consultant_Informational | Yes | 087100 | 1.7-A |  | Qualifications
Door Hardware_Each Type of Electrified Door Hardware_Informational | Yes | 087100 | 1.7-B |  | Certificate
Door Hardware_Product Test Reports_Informational | Yes | 087100 | 1.7-C |  | Report
Door Hardware_Field Quality-Control Reports_Informational | Yes | 087100 | 1.7-D |  | Report
Door Hardware_Special Warranty_Informational | Yes | 087100 | 1.7-E |  | Sample
Door Hardware_Hinges | Yes | 087100 | 2.3 |  | Product Data
Door Hardware_Lock Throw | Yes | 087100 | 2.4-B |  | Product Data
Door Hardware_Lock Backset | Yes | 087100 | 2.4-C |  | Product Data
Door Hardware_Lock Trim | Yes | 087100 | 2.4-D |  | Product Data
Door Hardware_Strikes | Yes | 087100 | 2.4-E |  | Product Data
Door Hardware_Bored Locks | Yes | 087100 | 2.4-F |  | Product Data
Door Hardware_Mortise Locks | Yes | 087100 | 2.4-G |  | Product Data
Door Hardware_Push-Pull Latches | Yes | 087100 | 2.4-H |  | Product Data
Door Hardware_Mortise Auxiliary Locks | Yes | 087100 | 2.5-A |  | Product Data
Door Hardware_Electromagnetic Locks | Yes | 087100 | 2.6-A |  | Product Data
Door Hardware_Exit Locks and Alarms | Yes | 087100 | 2.7-A |  | Product Data
Door Hardware_Manual Flush Bolts | Yes | 087100 | 2.8-A |  | Product Data
Door Hardware_Exit Devices and Auxiliary Items | Yes | 087100 | 2.9-A |  | Product Data
Door Hardware_Standard Lock Cylinders | Yes | 087100 | 2.10-A |  | Product Data
Door Hardware_High-Security Lock Cylinders | Yes | 087100 | 2.10-B |  | Product Data
Door Hardware_Construction Master Keys | Yes | 087100 | 2.10-C |  | Product Data
Door Hardware_Construction Cores | Yes | 087100 | 2.10-D |  | Product Data
Door Hardware_Keys | Yes | 087100 | 2.11-B-2 |  | Product Data
Door Hardware_Multiple-Drawer Cabinet | Yes | 087100 | 2.12-A-1 |  | Product Data
Door Hardware_Wall-Mounted Cabinet | Yes | 087100 | 2.12-A-2 |  | Product Data
Door Hardware_Portable Cabinet | Yes | 087100 | 2.12-A-3 |  | Product Data
Door Hardware_Operating Trim | Yes | 087100 | 2.13-A |  | Product Data
Door Hardware_Coordinators | Yes | 087100 | 2.14-A |  | Product Data
Door Hardware_Carry-Open Bars | Yes | 087100 | 2.14-B |  | Product Data
Door Hardware_Astragals | Yes | 087100 | 2.14-C |  | Product Data
Door Hardware_Surface Closers | Yes | 087100 | 2.15-A |  | Product Data
Door Hardware_Concealed Closers | Yes | 087100 | 2.16-A |  | Product Data
Door Hardware_Overhead Stops and Holders | Yes | 087100 | 2.17-A |  | Product Data
Door Hardware_Door Gasketing | Yes | 087100 | 2.18-A |  | Product Data
Door Hardware_Thresholds | Yes | 087100 | 2.19-A |  | Product Data
Door Hardware_Metal Protective Trim Units | Yes | 087100 | 2.20-A |  | Product Data
Door Hardware_Plastic Protection Plates | Yes | 087100 | 2.21-A |  | Product Data
Glazing_Insulating Glass | Yes | 088000 | 1.6-B |  | Sample
Glazing_Sealants | Yes | 088000 | 1.6-C |  | Sample
Glazing_Glazing Schedule | Yes | 088000 | 1.6-D |  | Schedule
Glazing_Delegated Design for Glass | Yes | 088000 | 1.6-E |  | Report
Glazing_Installer, Manufacturers Of Fabricated Glass Units, Glass Testing Agency and Sealant Testing Agency_Informational | Yes | 088000 | 1.7-A |  | Qualifications
Glazing_Glass_Informational | Yes | 088000 | 1.7-B |  | Certificate
Glazing_Fabricated Glass and Glazing Sealants_Informational | Yes | 088000 | 1.7-C |  | Report
Glazing_Preconstruction Adhesion and Compatibility Test Report_Informational | Yes | 088000 | 1.7-D |  | Report
Glazing_Special Warranties_Informational | Yes | 088000 | 1.7-E |  | Sample
Glazing_Glass Products | Yes | 088000 | 2.3 |  | Product Data
Glazing_Fully Tempered Float Glass | Yes | 088000 | 2.5-A |  | Product Data
Glazing_Heat-Strengthened Float Glass | Yes | 088000 | 2.5-B |  | Product Data
Glazing_Reflective and Low-E-Coated Vision Glass | Yes | 088000 | 2.5-C |  | Product Data
Glazing_Insulating-Glass Units | Yes | 088000 | 2.6-A |  | Product Data
Glazing_Glazing Sealants | Yes | 088000 | 2.7 |  | Product Data
Glazing_Back-Bedding Mastic Glazing Tapes | Yes | 088000 | 2.8-A |  | Product Data
Glazing_Expanded Cellular Glazing Tapes | Yes | 088000 | 2.8-B |  | Product Data
Glazing_Cleaners, Primers, and Sealers | Yes | 088000 | 2.9-B |  | Product Data
Glazing_Setting Blocks | Yes | 088000 | 2.9-C |  | Product Data
Glazing_Spacers | Yes | 088000 | 2.9-D |  | Product Data
Glazing_Edge Blocks | Yes | 088000 | 2.9-E |  | Product Data
Glazing_Cylindrical Glazing Sealant Backing | Yes | 088000 | 2.9-F |  | Product Data
Fire-Rated Glazing_Each Type of Glass Product | Yes | 088813 | 1.5-B |  | Sample
Fire-Rated Glazing_Glazing Schedule | Yes | 088813 | 1.5-C |  | Schedule
Fire-Rated Glazing_Installer and Glass Testing Agency | Yes | 088813 | 1.6-A |  | Qualifications
Fire-Rated Glazing_Each Type of Glass and Glazing Product | Yes | 088813 | 1.6-B |  | Certificate
Fire-Rated Glazing_Special Warranties | Yes | 088813 | 1.6-C |  | Sample
Fire-Rated Glazing_Glass Products | Yes | 088813 | 2.3 |  | Product Data
Fire-Rated Glazing_Ultraclear Float Glass | Yes | 088813 | 2.4-A |  | Product Data
Fire-Rated Glazing_Tempered Float Glass | Yes | 088813 | 2.4-B |  | Product Data
Fire-Rated Glazing_Fire-Protection-Rated Glazing | Yes | 088813 | 2.5-A |  | Product Data
Fire-Rated Glazing_Fire-Protection-Rated Glazing Labeling | Yes | 088813 | 2.5-B |  | Product Data
Fire-Rated Glazing_Fire-Protection-Rated Tempered Glass | Yes | 088813 | 2.5-C |  | Product Data
Fire-Rated Glazing_Fire-Protection-Rated Film-Faced Ceramic Glazing | Yes | 088813 | 2.5-D |  | Product Data
Fire-Rated Glazing_Fire-Resistance-Rated Glazing | Yes | 088813 | 2.6-A |  | Product Data
Fire-Rated Glazing_Fire-Resistance-Rated Glazing Labeling | Yes | 088813 | 2.6-B |  | Product Data
Fire-Rated Glazing_Fire-Resistance-Rated Framing and Doors | Yes | 088813 | 2.6-C |  | Product Data
Fire-Rated Glazing_Glazing Sealants for Fire-Rated Glazing Products | Yes | 088813 | 2.7-B |  | Product Data
Fire-Rated Glazing_Back-Bedding Mastic Glazing Tapes | Yes | 088813 | 2.7-C |  | Product Data
Fire-Rated Glazing_Expanded Cellular Glazing Tapes | Yes | 088813 | 2.7-D |  | Product Data
Fire-Rated Glazing_Cylindrical Glazing Sealant Backing | Yes | 088813 | 2.8-B |  | Product Data
Fire-Rated Glazing_Perimeter Insulation for Fire-Resistance-Rated Glazing | Yes | 088813 | 2.8-C |  | Product Data
Gypsum Board Shaft Wall Assemblies_Gypsum Shaftliner Board | Yes | 092116.23 | 2.2-C |  | Product Data
Gypsum Board Shaft Wall Assemblies_Non-Load-Bearing Steel Framing | Yes | 092116.23 | 2.2-D |  | Product Data
Gypsum Board Shaft Wall Assemblies_Studs | Yes | 092116.23 | 2.2-E |  | Product Data
Gypsum Board Shaft Wall Assemblies_Runner Tracks | Yes | 092116.23 | 2.2-F |  | Product Data
Gypsum Board Shaft Wall Assemblies_Firestop Tracks | Yes | 092116.23 | 2.2-G |  | Product Data
Gypsum Board Shaft Wall Assemblies_Elevator-Hoistway-Entrance Struts | Yes | 092116.23 | 2.2-H |  | Product Data
Gypsum Board Shaft Wall Assemblies_Finish Panels | Yes | 092116.23 | 2.2-I |  | Product Data
Gypsum Board Shaft Wall Assemblies_Sound Attenuation Blankets | Yes | 092116.23 | 2.2-J |  | Product Data
Gypsum Board Shaft Wall Assemblies_Trim Accessories | Yes | 092116.23 | 2.3-B |  | Product Data
Gypsum Board Shaft Wall Assemblies_Steel Drill Screws | Yes | 092116.23 | 2.3-C |  | Product Data
Gypsum Board Shaft Wall Assemblies_Track Fasteners | Yes | 092116.23 | 2.3-D |  | Product Data
Gypsum Board Shaft Wall Assemblies_Reinforcing | Yes | 092116.23 | 2.3-E |  | Product Data
Gypsum Board Shaft Wall Assemblies_Acoustical Sealant | Yes | 092116.23 | 2.3-F |  | Product Data
Gypsum Board Shaft Wall Assemblies_Gypsum Board Cants | Yes | 092116.23 | 2.3-G |  | Product Data
Non-Structural Metal Framing_Code-Compliance Certification for Studs and Tracks_Informational | Yes | 092216 | 1.4-A |  | Certificate
Non-Structural Metal Framing_for Embossed, High-Strength Steel Studs and Tracks, Firestop Tracks and Power-Actuated Fasteners_Informational | Yes | 092216 | 1.4-B |  | Report
Non-Structural Metal Framing_Framing Members | Yes | 092216 | 2.2-A |  | Product Data
Non-Structural Metal Framing_Studs and Tracks | Yes | 092216 | 2.2-B |  | Product Data
Non-Structural Metal Framing_Slip-Type Head Joints | Yes | 092216 | 2.2-C |  | Product Data
Non-Structural Metal Framing_Firestop Tracks | Yes | 092216 | 2.2-D |  | Product Data
Non-Structural Metal Framing_Flat Strap and Backing Plate | Yes | 092216 | 2.2-E |  | Product Data
Non-Structural Metal Framing_Cold-Rolled Channel Bridging | Yes | 092216 | 2.2-F |  | Product Data
Non-Structural Metal Framing_Hat-Shaped, Rigid Furring Channels | Yes | 092216 | 2.2-G |  | Product Data
Non-Structural Metal Framing_Cold-Rolled Furring Channels | Yes | 092216 | 2.2-H |  | Product Data
Non-Structural Metal Framing_Z-Shaped Furring | Yes | 092216 | 2.2-I |  | Product Data
Non-Structural Metal Framing_Tie Wire | Yes | 092216 | 2.3-A |  | Product Data
Non-Structural Metal Framing_Post-Installed Anchors | Yes | 092216 | 2.3-B-1 |  | Product Data
Non-Structural Metal Framing_Power-Actuated Anchors | Yes | 092216 | 2.3-B-2 |  | Product Data
Non-Structural Metal Framing_Wire Hangers | Yes | 092216 | 2.3-C |  | Product Data
Non-Structural Metal Framing_Flat Hangers | Yes | 092216 | 2.3-D |  | Product Data
Non-Structural Metal Framing_Carrying Channels (Main Runners) | Yes | 092216 | 2.3-E |  | Product Data
Non-Structural Metal Framing_Furring Channels (Furring Members) | Yes | 092216 | 2.3-F |  | Product Data
Non-Structural Metal Framing_Grid Suspension System for Gypsum Board Ceilings | Yes | 092216 | 2.3-G |  | Product Data
Non-Structural Metal Framing_Isolation Strip at Exterior Walls | Yes | 092216 | 2.4-B |  | Product Data
Gypsum Board_Gypsum Wallboard | Yes | 092900 | 1.3-A-1 |  | Product Data
Gypsum Board_Gypsum Board, Type X | Yes | 092900 | 1.3-A-2 |  | Product Data
Gypsum Board_Impact-Resistant Gypsum Board | Yes | 092900 | 1.3-A-3 |  | Product Data
Gypsum Board_Mold-Resistant Gypsum Board | Yes | 092900 | 1.3-A-4 |  | Product Data
Gypsum Board_Acoustically Enhanced Gypsum Board | Yes | 092900 | 1.3-A-5 |  | Product Data
Gypsum Board_Cementitious Backer Units | Yes | 092900 | 1.3-A-6 |  | Product Data
Gypsum Board_Interior Trim | Yes | 092900 | 1.3-A-7 |  | Product Data
Gypsum Board_Joint Treatment Materials | Yes | 092900 | 1.3-A-8 |  | Product Data
Gypsum Board_Sound-Attenuation Blankets | Yes | 092900 | 1.3-A-9 |  | Product Data
Gypsum Board_Acoustical Sealant | Yes | 092900 | 1.3-A-10 |  | Product Data
Gypsum Board_Trim Accessories | Yes | 092900 | 1.3-B-1 |  | Sample
Ceramic Tiling_Each Type Of Tile and Tile Pattern | Yes | 093013 | 1.5-B |  | Shop Drawings
Ceramic Tiling_Full-Size Units ff Each Type and Composition of Tile | Yes | 093013 | 1.5-C-1 |  | Sample
Ceramic Tiling_Marble Thresholds In 6-Inch Lengths | Yes | 093013 | 1.5-C-2 |  | Sample
Ceramic Tiling_Installer_Informational | Yes | 093013 | 1.6-A |  | Qualifications
Ceramic Tiling_Shipment, Type, and Composition of Tile_Informational | Yes | 093013 | 1.6-B |  | Certificate
Ceramic Tiling_Product Certificates_Informational | Yes | 093013 | 1.6-C |  | Certificate
Ceramic Tiling_Tile-Setting and Grouting Products_Informational | Yes | 093013 | 1.6-D |  | Test Data
Ceramic Tiling_Glazed Porcelain Tile (TL-1) | Yes | 093013 | 2.3-A |  | Product Data
Ceramic Tiling_Glazed Wall Tile (TL-2) | Yes | 093013 | 2.3-B |  | Product Data
Ceramic Tiling_Glazed Wall Tile (TL-3) | Yes | 093013 | 2.3-C |  | Product Data
Ceramic Tiling_Glazed Porcelain Tile (TL-4) | Yes | 093013 | 2.3-D |  | Product Data
Ceramic Tiling_Marble Thresholds | Yes | 093013 | 2.4-B |  | Product Data
Ceramic Tiling_Fabric-Reinforced, Fluid-Applied Membrane | Yes | 093013 | 2.5-B |  | Product Data
Ceramic Tiling_Crack Isolation Membrane | Yes | 093013 | 2.6 |  | Product Data
Ceramic Tiling_Portland Cement Mortar (Thickset) Installation Materials | Yes | 093013 | 2.7-A |  | Product Data
Ceramic Tiling_Standard Dry-Set Mortar (Thinset) | Yes | 093013 | 2.7-B |  | Product Data
Ceramic Tiling_Sand-Portland Cement Grout | Yes | 093013 | 2.8-A |  | Product Data
Ceramic Tiling_Standard Cement Grout | Yes | 093013 | 2.8-B |  | Product Data
Ceramic Tiling_Water-Cleanable Epoxy Grout | Yes | 093013 | 2.8-C |  | Product Data
Ceramic Tiling_Trowelable Underlayments and Patching Compounds | Yes | 093013 | 2.9-A |  | Product Data
Ceramic Tiling_Floor Sealer | Yes | 093013 | 2.9-B |  | Product Data
Acoustical Panel Ceilings_Each Exposed Product and for Each Color and Texture Specified | Yes | 095113 | 1.4-B |  | Sample
Acoustical Panel Ceilings_Each Component Indicated and for Each Exposed Finish Required | Yes | 095113 | 1.4-C |  | Sample
Acoustical Panel Ceilings_Seismic Restraints for Ceiling Systems | Yes | 095113 | 1.4-D |  | Leed Requirements
Acoustical Panel Ceilings_Coordination Drawings_Informational | Yes | 095113 | 1.5-A |  | Record Drawing
Acoustical Panel Ceilings_Testing Agency_Informational | Yes | 095113 | 1.5-B |  | Qualifications
Acoustical Panel Ceilings_Each Acoustical Panel Ceiling_Informational | Yes | 095113 | 1.5-C |  | Test Data
Acoustical Panel Ceilings_Each Acoustical Panel Ceiling Suspension System and Anchor and Fastener Type_Informational | Yes | 095113 | 1.5-D |  | Report
Acoustical Panel Ceilings_Field Quality-Control Reports_Informational | Yes | 095113 | 1.5-E |  | Report
Acoustical Panel Ceilings_Acoustical Panels ACP-1 | Yes | 095113 | 2.3 |  | Product Data
Acoustical Panel Ceilings_Acoustical Panels ACP-2 | Yes | 095113 | 2.4 |  | Product Data
Acoustical Panel Ceilings_Acoustical Panels ACP-3 | Yes | 095113 | 2.5 |  | Product Data
Acoustical Panel Ceilings_Wood Grille WDG-1 | Yes | 095113 | 2.6 |  | Product Data
Acoustical Panel Ceilings_Metal Suspension System ACP-1 | Yes | 095113 | 2.7 |  | Product Data
Acoustical Panel Ceilings_Metal Suspension System ACP-2 | Yes | 095113 | 2.8 |  | Product Data
Acoustical Panel Ceilings_Metal Suspension System ACP-3 | Yes | 095113 | 2.9 |  | Product Data
Acoustical Panel Ceilings_Attachment Devices | Yes | 095113 | 2.10-A |  | Product Data
Acoustical Panel Ceilings_Wire Hangers, Braces, and Ties | Yes | 095113 | 2.10-B |  | Product Data
Acoustical Panel Ceilings_Hanger Rods | Yes | 095113 | 2.10-C |  | Product Data
Acoustical Panel Ceilings_Flat Hangers | Yes | 095113 | 2.10-D |  | Product Data
Acoustical Panel Ceilings_Angle Hangers | Yes | 095113 | 2.10-E |  | Product Data
Acoustical Panel Ceilings_Seismic Clips | Yes | 095113 | 2.10-F |  | Product Data
Acoustical Panel Ceilings_Seismic Stabilizer Bars | Yes | 095113 | 2.10-G |  | Product Data
Acoustical Panel Ceilings_Seismic Struts | Yes | 095113 | 2.10-H |  | Product Data
Acoustical Panel Ceilings_Roll-formed, Sheet-Metal Edge Moldings and Trim | Yes | 095113 | 2.11-A |  | Product Data
Acoustical Panel Ceilings_Extruded-Aluminum Edge Moldings and Trim | Yes | 095113 | 2.11-B |  | Product Data
Acoustical Panel Ceilings_Acoustical Sealant | Yes | 095113 | 2.12-A |  | Product Data
Resilient Base and Accessories_Each Exposed Product and for Each Color and Texture Specified | Yes | 096513 | 1.3-B |  | Sample
Resilient Base and Accessories_Each Type Of Product Indicated and for Each Color, Texture, and Pattern | Yes | 096513 | 1.3-C |  | Sample
Resilient Base and Accessories_Resilient Base and Accessory Products | Yes | 096513 | 1.3-D |  | Schedule
Resilient Base and Accessories_Thermoset-Rubber Base (RBB 1 - 4) | Yes | 096513 | 2.1 |  | Product Data
Resilient Base and Accessories_Trowelable Leveling and Patching Compounds | Yes | 096513 | 2.3-A |  | Product Data
Resilient Base and Accessories_Adhesives | Yes | 096513 | 2.3-B |  | Product Data
Resilient Sheet Flooring_Resilient Sheet Flooring | Yes | 096516 | 1.3-B |  | Shop Drawings
Resilient Sheet Flooring_Heat-Welding Bead | Yes | 096516 | 1.3-C-1 |  | Sample
Resilient Sheet Flooring_Welded-Seam | Yes | 096516 | 1.3-E-1 |  | Sample
Resilient Sheet Flooring_Resilient Sheet Flooring | Yes | 096516 | 1.3-F |  | Schedule
Resilient Sheet Flooring_Installer_Informational | Yes | 096516 | 1.4-A |  | Qualifications
Resilient Sheet Flooring_Unbacked Vinyl Sheet Flooring (VS-1) | Yes | 096516 | 2.2 |  | Product Data
Resilient Sheet Flooring_Unbacked Vinyl Sheet Flooring (VS-2 ) | Yes | 096516 | 2.3 |  | Product Data
Resilient Sheet Flooring_Trowelable Leveling and Patching Compounds | Yes | 096516 | 2.4-A |  | Product Data
Resilient Sheet Flooring_Adhesives | Yes | 096516 | 2.4-B |  | Product Data
Resilient Sheet Flooring_Heat-Welding Bead | Yes | 096516 | 2.4-C |  | Product Data
Resilient Sheet Flooring_Integral Flash Cove Strip | Yes | 096516 | 2.4-D-1 |  | Product Data
Resilient Sheet Flooring_Integral Flash Cap Strip | Yes | 096516 | 2.4-D-2 |  | Product Data
Resilient Sheet Flooring_Integral Flash Corners | Yes | 096516 | 2.4-D-3 |  | Product Data
Resilient Sheet Flooring_Floor Polish | Yes | 096516 | 2.4-E |  | Product Data
Resilient Tile Flooring_Resilient Tile Flooring | Yes | 096519 | 1.3-B |  | Shop Drawings
Resilient Tile Flooring_Heat-Welding Bead | Yes | 096519 | 1.3-C-1 |  | Sample
Resilient Tile Flooring_Floor Tile | Yes | 096519 | 1.3-E |  | Schedule
Resilient Tile Flooring_Installer_Informational | Yes | 096519 | 1.4-A |  | Qualifications
Resilient Tile Flooring_Luxury Vinyl Floor Tile (LVT-1) | Yes | 096519 | 2.2 |  | Product Data
Resilient Tile Flooring_Rubber Floor Tile (RBT-1) | Yes | 096519 | 2.3 |  | Product Data
Resilient Tile Flooring_Vinyl Composition Floor Tile (VCT-1) | Yes | 096519 | 2.4 |  | Product Data
Resilient Tile Flooring_Vinyl Composition Floor Tile (VCT-2) | Yes | 096519 | 2.5 |  | Product Data
Resilient Tile Flooring_Trowelable Leveling and Patching Compounds | Yes | 096519 | 2.6-A |  | Product Data
Resilient Tile Flooring_Adhesives | Yes | 096519 | 2.6-B |  | Product Data
Resilient Tile Flooring_Floor Polish | Yes | 096519 | 2.6-C |  | Product Data
Resilient Athletic Flooring_Resilient Athletic Flooring | Yes | 096566 | 1.4-B |  | Shop Drawings
Resilient Athletic Flooring_Game-Line and Marker-Paint | Yes | 096566 | 1.4-C-1 |  | Sample
Resilient Athletic Flooring_Vinyl Sheet Flooring Seam | Yes | 096566 | 1.4-C-2 |  | Sample
Resilient Athletic Flooring_Interlocking, Rubber Floor Tile | Yes | 096566 | 2.1 |  | Product Data
Resilient Athletic Flooring_Trowelable Leveling and Patching Compound | Yes | 096566 | 2.2-A |  | Product Data
Resilient Athletic Flooring_Adhesives | Yes | 096566 | 2.2-B |  | Product Data
Resilient Athletic Flooring_Game-Line and Marker Paint | Yes | 096566 | 2.2-C |  | Product Data
Resinous Matrix Terrazzo Flooring_Terrazzo Flooring | Yes | 096623 | 1.4-B |  | Shop Drawings
Resinous Matrix Terrazzo Flooring_Terrazzo Flooring | Yes | 096623 | 1.4-C |  | Sample
Resinous Matrix Terrazzo Flooring_Precast Terrazzo | Yes | 096623 | 1.4-D-1 |  | Sample
Resinous Matrix Terrazzo Flooring_Exposed Strip Item | Yes | 096623 | 1.4-D-2 |  | Sample
Resinous Matrix Terrazzo Flooring_Installer_Informational | Yes | 096623 | 1.5-A |  | Qualifications
Resinous Matrix Terrazzo Flooring_Terrazo Material_Informational | Yes | 096623 | 1.5-B |  | Certificate
Resinous Matrix Terrazzo Flooring_Manufacturer'S Installer_Informational | Yes | 096623 | 1.5-C |  | Certificate
Resinous Matrix Terrazzo Flooring_Preinstallation Moisture-Testing Reports_Informational | Yes | 096623 | 1.5-D |  | Report
Resinous Matrix Terrazzo Flooring_Precast Terrazzo Units TRZ-1 | Yes | 096623 | 2.3-B |  | Product Data
Resinous Matrix Terrazzo Flooring_Abrasive Strips | Yes | 096623 | 2.4-A |  | Product Data
Resinous Matrix Terrazzo Flooring_Strip Adhesives | Yes | 096623 | 2.5-A |  | Product Data
Resinous Matrix Terrazzo Flooring_Strip Anchoring Device | Yes | 096623 | 2.5-B-1 |  | Product Data
Resinous Matrix Terrazzo Flooring_Precast Terraro Anchoring Device | Yes | 096623 | 2.5-B-2 |  | Product Data
Resinous Matrix Terrazzo Flooring_Patching and Fill Material | Yes | 096623 | 2.5-C |  | Product Data
Resinous Matrix Terrazzo Flooring_Joint Compound | Yes | 096623 | 2.5-D |  | Product Data
Resinous Matrix Terrazzo Flooring_Resinous Matrix Terrazzo Cleaner | Yes | 096623 | 2.5-E |  | Product Data
Resinous Matrix Terrazzo Flooring_Sealer | Yes | 096623 | 2.5-F |  | Product Data
Tile Carpeting_Carpet Tile | Yes | 096813 | 1.4-B |  | Shop Drawings
Tile Carpeting_Carpet Tile | Yes | 096813 | 1.4-C-1 |  | Sample
Tile Carpeting_Exposed Edge, Transition, and Other Accessory Stripping | Yes | 096813 | 1.4-C-1 |  | Sample
Tile Carpeting_Carpet Tile | Yes | 096813 | 1.4-E |  | Schedule
Tile Carpeting_Sustainable Product Certification | Yes | 096813 | 1.4-F |  | Certificate
Tile Carpeting_Installer_Informational | Yes | 096813 | 1.5-A |  | Qualifications
Tile Carpeting_Carpet Tile Product Test Report_Informational | Yes | 096813 | 1.5-B |  | Report
Tile Carpeting_Carpet Tile Warranty_Informational | Yes | 096813 | 1.5-C |  | Warranty
Tile Carpeting_Carpet Tile (CPT-1) | Yes | 096813 | 2.1 |  | Product Data
Tile Carpeting_Carpet Tile (CPT-2) | Yes | 096813 | 2.2 |  | Product Data
Tile Carpeting_Carpet Tile (CPT-3) | Yes | 096813 | 2.3 |  | Product Data
Tile Carpeting_Trowelable Leveling and Patching Compounds | Yes | 096813 | 2.4-A |  | Product Data
Tile Carpeting_Adhesives | Yes | 096813 | 2.4-B |  | Product Data
Tile Carpeting_Metal Edge/Transition Strips | Yes | 096813 | 2.4-C |  | Product Data
Wall Coverings_Wall Covering | Yes | 097200 | 1.3-B |  | Shop Drawings
Wall Coverings_Wall Covering | Yes | 097200 | 1.3-C |  | Sample
Wall Coverings_Wall Covering | Yes | 097200 | 1.3-D |  | Schedule
Wall Coverings_Wall Covering Product Test Report_Informational | Yes | 097200 | 1.4-A |  | Report
Wall Coverings_Vinyl Wall & Floor Film (FL-1, FL-2, FL-3, FL-4, FL-5, FL-6) | Yes | 097200 | 2.2 |  | Product Data
Wall Coverings_Textile Wall Covering (WC-1, SF-1, SF-2, SF-3) | Yes | 097200 | 2.3 |  | Product Data
Stretched-Fabric Wall Systems_Stretched Fabric System | Yes | 097713 | 1.5-B |  | Shop Drawings
Stretched-Fabric Wall Systems_Fabric | Yes | 097713 | 1.5-C-1 |  | Sample
Stretched-Fabric Wall Systems_Frame System | Yes | 097713 | 1.5-C-2 |  | Sample
Stretched-Fabric Wall Systems_Core Material | Yes | 097713 | 1.5-C-3 |  | Sample
Stretched-Fabric Wall Systems_Assembled System | Yes | 097713 | 1.5-C-4 |  | Sample
Stretched-Fabric Wall Systems_Electrical Coordination Drawings_Informational | Yes | 097713 | 1.6-A |  | Record Drawing
Stretched-Fabric Wall Systems_Installer_Informational | Yes | 097713 | 1.6-B |  | Certificate
Stretched-Fabric Wall Systems_Stretched Fabric System Product Certificate_Informational | Yes | 097713 | 1.6-C |  | Certificate
Stretched-Fabric Wall Systems_Stretched Fabric System_Informational | Yes | 097713 | 1.6-D |  | Warranty
Stretched-Fabric Wall Systems_Stretched-Fabric Wall System FWP-1 | Yes | 097713 | 2.3-A |  | Product Data
Stretched-Fabric Wall Systems_Glass-Fiber Board | Yes | 097713 | 2.4-A-1 |  | Product Data
Stretched-Fabric Wall Systems_Impact-Resistant, Acoustically Transparent, Copolymer Sheet for Face Layer | Yes | 097713 | 2.4-A-2 |  | Product Data
Stretched-Fabric Wall Systems_Facing Material | Yes | 097713 | 2.4-C |  | Product Data
Stretched-Fabric Wall Systems_Lining Material | Yes | 097713 | 2.4-D |  | Product Data
Stretched-Fabric Wall Systems_Adhesives | Yes | 097713 | 2.5-A-1 |  | Product Data
Stretched-Fabric Wall Systems_Fasteners | Yes | 097713 | 2.5-A-3 |  | Product Data
Exterior Painting_Paint System & Each Color and Gloss of Topcoat | Yes | 099113 | 1.4-B |  | Sample
Exterior Painting_Paint Product List | Yes | 099113 | 1.4-C |  | Report
Exterior Painting_Exterior Paint | Yes | 099113 | 2.2 |  | Product Data
Interior Painting_Paint System & Each Color and Gloss of Topcoat | Yes | 099123 | 1.4-B |  | Sample
Interior Painting_Paint Product List | Yes | 099123 | 1.4-C |  | Report
Interior Painting_Interior Paint | Yes | 099123 | 2.2 |  | Product Data
Interior Painting_Primer Sealer, Latex, Interior | Yes | 099123 | 2.3-A |  | Product Data
Interior Painting_Latex, Interior, Institutional Low Odor/VOC (Gloss Level 3) | Yes | 099123 | 2.4-A |  | Product Data
High-Performance Coatings_Coating System & Each Color and Gloss of Topcoat | Yes | 099600 | 1.4-B |  | Sample
High-Performance Coatings_Paint Product List | Yes | 099600 | 1.4-C |  | Report
High-Performance Coatings_High-Performance Coatings | Yes | 099600 | 2.2 |  | Product Data
Cementitious Coatings_Color and Gloss of Topcoat | Yes | 099726 | 1.3-B |  | Sample
Cementitious Coatings_Material Certificates | Yes | 099726 | 1.4-A |  | Certificate
Cementitious Coatings_Product Test Reports | Yes | 099726 | 1.4-B |  | Report
Cementitious Coatings_Polymer-Modified Cementitious Coating | Yes | 099726 | 2.2-A |  | Product Data
Cementitious Coatings_Crack, Block Fillers and other Materials | Yes | 099726 | 2.2-C |  | Product Data
Stainless-Steel Toilet Compartments_Toilet Compartments | Yes | 102113.14 | 1.3-B |  | Shop Drawings
Stainless-Steel Toilet Compartments_Hardware and Accessories | Yes | 102113.14 | 1.3-C-1 |  | Sample
Stainless-Steel Toilet Compartments_Material, Color, and Finish Toilet Compartments | Yes | 102113.14 | 1.3-D-1 |  | Sample
Stainless-Steel Toilet Compartments_Hardware and Accessory Samples for Verification | Yes | 102113.14 | 1.3-D-1 |  | Sample
Stainless-Steel Toilet Compartments_Toilet Compartments | Yes | 102113.14 | 1.3-E |  | Schedule
Stainless-Steel Toilet Compartments_Product Certificates | Yes | 102113.14 | 1.4-A |  | Certificate
Stainless-Steel Toilet Compartments_Stainless Steel Toilet Compartments | Yes | 102113.14 | 2.2 |  | Product Data
Stainless-Steel Toilet Compartments_Hinges | Yes | 102113.14 | 2.3-A-1 |  | Product Data
Stainless-Steel Toilet Compartments_Latch and Keeper | Yes | 102113.14 | 2.3-A-2 |  | Product Data
Stainless-Steel Toilet Compartments_Coat Hook | Yes | 102113.14 | 2.3-A-3 |  | Product Data
Stainless-Steel Toilet Compartments_Door Bumper | Yes | 102113.14 | 2.3-A-4 |  | Product Data
Stainless-Steel Toilet Compartments_Door Pull | Yes | 102113.14 | 2.3-A-5 |  | Product Data
Stainless-Steel Toilet Compartments_Overhead Bracing | Yes | 102113.14 | 2.3-B |  | Product Data
Stainless-Steel Toilet Compartments_Anchorages and Fasteners | Yes | 102113.14 | 2.3-C |  | Product Data
Stainless-Steel Toilet Compartments_Stainless Steel Sheet | Yes | 102113.14 | 2.4-A |  | Product Data
Stainless-Steel Toilet Compartments_Stainless Steel Castings | Yes | 102113.14 | 2.4-B |  | Product Data
Wire Mesh Partitions_Wire Mesh Partitions | Yes | 102213 | 1.4-B |  | Shop Drawings
Wire Mesh Partitions_Wire Mesh | Yes | 102213 | 1.4-C |  | Sample
Wire Mesh Partitions_Installer_Informational | Yes | 102213 | 1.5-A |  | Qualifications
Wire Mesh Partitions_Welding Certificates_Informational | Yes | 102213 | 1.5-B |  | Certificate
Wire Mesh Partitions_Steel Wire | Yes | 102213 | 2.3-B |  | Product Data
Wire Mesh Partitions_Steel Plates, Channels, Angles, and Bars | Yes | 102213 | 2.3-C |  | Product Data
Wire Mesh Partitions_Steel Sheet | Yes | 102213 | 2.3-D |  | Product Data
Wire Mesh Partitions_Steel Pipe | Yes | 102213 | 2.3-E |  | Product Data
Wire Mesh Partitions_Steel Tubing | Yes | 102213 | 2.3-F |  | Product Data
Wire Mesh Partitions_Metallic-Coated Steel Sheet | Yes | 102213 | 2.3-G |  | Product Data
Wire Mesh Partitions_Panel-to-Panel Fasteners | Yes | 102213 | 2.3-H |  | Product Data
Wire Mesh Partitions_Post-Installed Anchors | Yes | 102213 | 2.3-I |  | Product Data
Wire Mesh Partitions_Power-Driven Fasteners | Yes | 102213 | 2.3-J |  | Product Data
Wire Mesh Partitions_Seismic Bracing | Yes | 102213 | 2.3-K |  | Product Data
Wire Mesh Partitions_Universal Shop Primer | Yes | 102213 | 2.3-L |  | Product Data
Wire Mesh Partitions_Zinc-Rich Primer | Yes | 102213 | 2.3-M |  | Product Data
Wire Mesh Partitions_Galvanizing Repair Paint | Yes | 102213 | 2.3-N |  | Product Data
Wire Mesh Partitions_Mesh | Yes | 102213 | 2.4-A |  | Product Data
Wire Mesh Partitions_Vertical and Horizontal Panel Framing | Yes | 102213 | 2.4-B |  | Product Data
Wire Mesh Partitions_Horizontal Panel Stiffeners | Yes | 102213 | 2.4-C |  | Product Data
Wire Mesh Partitions_Top Capping Bars | Yes | 102213 | 2.4-D |  | Product Data
Wire Mesh Partitions_Posts for 90-Degree Corners | Yes | 102213 | 2.4-E |  | Product Data
Wire Mesh Partitions_Posts for Other-Than-90-Degree Corners | Yes | 102213 | 2.4-F |  | Product Data
Wire Mesh Partitions_Adjustable Corner Posts | Yes | 102213 | 2.4-G |  | Product Data
Wire Mesh Partitions_Line Posts | Yes | 102213 | 2.4-H |  | Product Data
Wire Mesh Partitions_Three- and Four-Way Intersection Posts | Yes | 102213 | 2.4-I |  | Product Data
Wire Mesh Partitions_Floor Shoes | Yes | 102213 | 2.4-J |  | Product Data
Wire Mesh Partitions_Sliding Doors | Yes | 102213 | 2.4-K |  | Product Data
Demountable Partitions_Demountable Partitions | Yes | 102219 | 1.4-B |  | Shop Drawings
Demountable Partitions_Face-Panel Finish | Yes | 102219 | 1.4-C-1 |  | Sample
Demountable Partitions_Linear Trim | Yes | 102219 | 1.4-C-2 |  | Sample
Demountable Partitions_Door Finish | Yes | 102219 | 1.4-C-3 |  | Sample
Demountable Partitions_Glazing | Yes | 102219 | 1.4-C-4 |  | Sample
Demountable Partitions_Hardware and Accessories | Yes | 102219 | 1.4-C-5 |  | Sample
Demountable Partitions_RCP Coordination Drawings_Informational | Yes | 102219 | 1.5-A |  | Record Drawing
Demountable Partitions_Installer_Informational | Yes | 102219 | 1.5-B |  | Qualifications
Demountable Partitions_Product Certificates_Informational | Yes | 102219 | 1.5-C |  | Certificate
Demountable Partitions_Product Test Reports_Informational | Yes | 102219 | 1.5-D |  | Report
Demountable Partitions_Site-Assembled Demountable Partitions DMP-1 | Yes | 102219 | 2.2 |  | Product Data
Accordion Folding Partitions_Accordion Folding Partitions | Yes | 102233 | 1.5-B |  | Shop Drawings
Accordion Folding Partitions_Textile Facing Material | Yes | 102233 | 1.5-C-1 |  | Sample
Accordion Folding Partitions_Facing Material other Than Textile | Yes | 102233 | 1.5-C-2 |  | Sample
Accordion Folding Partitions_Edge Material | Yes | 102233 | 1.5-C-3 |  | Sample
Accordion Folding Partitions_Hardware | Yes | 102233 | 1.5-C-4 |  | Sample
Accordion Folding Partitions_Seismic Bracing Delegated Design Submittal | Yes | 102233 | 1.5-D |  | Report
Accordion Folding Partitions_RCP Coordination Drawings_Informational | Yes | 102233 | 1.6-A |  | Record Drawing
Accordion Folding Partitions_Embedded Items and Cutouts Setting Drawings_Informational | Yes | 102233 | 1.6-B |  | Shop Drawings
Accordion Folding Partitions_Installer_Informational | Yes | 102233 | 1.6-C |  | Qualifications
Accordion Folding Partitions_Product Certificates_Informational | Yes | 102233 | 1.6-D |  | Certificate
Accordion Folding Partitions_Material Certificates_Informational | Yes | 102233 | 1.6-E |  | Certificate
Accordion Folding Partitions_Product Test Reports_Informational | Yes | 102233 | 1.6-F |  | Report
Accordion Folding Partitions_Field Quality-Control Reports_Informational | Yes | 102233 | 1.6-G |  | Report
Accordion Folding Partitions_Special Warranty_Informational | Yes | 102233 | 1.6-H |  | Warranty
Accordion Folding Partitions_Accordion Folding Partition (AFP-1) | Yes | 102233 | 2.2 |  | Product Data
Accordion Folding Partitions_Seals | Yes | 102233 | 2.3-A |  | Product Data
Accordion Folding Partitions_Hardware | Yes | 102233 | 2.3-B |  | Product Data
Accordion Folding Partitions_Trim | Yes | 102233 | 2.3-C |  | Product Data
Accordion Folding Partitions_Lifting Cable | Yes | 102233 | 2.4-A |  | Product Data
Accordion Folding Partitions_Switches and Accessories | Yes | 102233 | 2.4-B |  | Product Data
Accordion Folding Partitions_Electric Operators | Yes | 102233 | 2.5 |  | Product Data
Accordion Folding Partitions_Facing Materials | Yes | 102233 | 2.6 |  | Product Data
Folding Glass-Panel Partitions_Operable Glass-Panel Partitions | Yes | 102239.13 | 1.5-B |  | Shop Drawings
Folding Glass-Panel Partitions_Panel Edge Material | Yes | 102239.13 | 1.5-C-1 |  | Sample
Folding Glass-Panel Partitions_Glass | Yes | 102239.13 | 1.5-C-2 |  | Sample
Folding Glass-Panel Partitions_Hardware | Yes | 102239.13 | 1.5-C-3 |  | Sample
Folding Glass-Panel Partitions_Seismic Restraints Delegated-Design Submittal | Yes | 102239.13 | 1.5-D |  | Report
Folding Glass-Panel Partitions_RCP Coordination Drawings_Informational | Yes | 102239.13 | 1.6-A |  | Record Drawing
Folding Glass-Panel Partitions_Embedded Items and Cutouts Setting Drawings_Informational | Yes | 102239.13 | 1.6-B |  | Shop Drawings
Folding Glass-Panel Partitions_Installer_Informational | Yes | 102239.13 | 1.6-C |  | Qualifications
Folding Glass-Panel Partitions_Seismic Qualification Certificates_Informational | Yes | 102239.13 | 1.6-D |  | Certificate
Folding Glass-Panel Partitions_Product Certificates_Informational | Yes | 102239.13 | 1.6-E |  | Certificate
Folding Glass-Panel Partitions_Product Test Reports_Informational | Yes | 102239.13 | 1.6-F |  | Report
Folding Glass-Panel Partitions_Sample Warranty_Informational | Yes | 102239.13 | 1.6-G |  | Warranty
Folding Glass-Panel Partitions_Operable Glass Panels (FGP-1) | Yes | 102239.13 | 2.2 |  | Product Data
Folding Glass-Panel Partitions_Seals | Yes | 102239.13 | 2.3 |  | Product Data
Folding Glass-Panel Partitions_Tracks | Yes | 102239.13 | 2.4-A |  | Product Data
Folding Glass-Panel Partitions_Carriers | Yes | 102239.13 | 2.4-B |  | Product Data
Folding Glass-Panel Partitions_Track Intersections, Switches, and Accessories | Yes | 102239.13 | 2.4-C |  | Product Data
Folding Glass-Panel Partitions_Pass Doors | Yes | 102239.13 | 2.5-A |  | Product Data
Wall and Door Protection_Wall and Door Protection | Yes | 102600 | 1.3-B |  | Shop Drawings
Wall and Door Protection_Wall Guards | Yes | 102600 | 1.3-C-1 |  | Sample
Wall and Door Protection_Corner Guards | Yes | 102600 | 1.3-C-2 |  | Sample
Wall and Door Protection_Handrail Product Certificate_Informational | Yes | 102600 | 1.4-A |  | Certificate
Wall and Door Protection_Material Certificate_Informational | Yes | 102600 | 1.4-B |  | Certificate
Wall and Door Protection_Sample Warranty_Informational | Yes | 102600 | 1.4-C |  | Warranty
Wall and Door Protection_Crash Rail WP-1 | Yes | 102600 | 2.3-A |  | Product Data
Wall and Door Protection_Surface-Mounted, Metal Corner Guards CG-1 | Yes | 102600 | 2.4-A |  | Product Data
Wall and Door Protection_Fasteners | Yes | 102600 | 2.5-A |  | Product Data
Wall and Door Protection_Adhesive | Yes | 102600 | 2.5-B |  | Product Data
Toilet, Bath, and Laundry Accessories_All Exposed Product | Yes | 102800 | 1.5-B |  | Sample
Toilet, Bath, and Laundry Accessories_Schedule of Items and Locations | Yes | 102800 | 1.5-C |  | Schedule
Toilet, Bath, and Laundry Accessories_Grab Bar Delegated-Design Submittal | Yes | 102800 | 1.5-D |  | Report
Toilet, Bath, and Laundry Accessories_Sample Warranty_Informational | Yes | 102800 | 1.6-A |  | Warranty
Toilet, Bath, and Laundry Accessories_Toilet Tissue (Roll) Dispenser | Yes | 102800 | 2.2-B |  | Product Data
Toilet, Bath, and Laundry Accessories_Paper Towel (Folded) Dispenser | Yes | 102800 | 2.2-C |  | Product Data
Toilet, Bath, and Laundry Accessories_Waste Receptacle | Yes | 102800 | 2.2-D |  | Product Data
Toilet, Bath, and Laundry Accessories_Automatic Soap Dispenser | Yes | 102800 | 2.2-E |  | Product Data
Toilet, Bath, and Laundry Accessories_Grab Bar | Yes | 102800 | 2.2-F |  | Product Data
Toilet, Bath, and Laundry Accessories_Seat-Cover Dispenser | Yes | 102800 | 2.2-G |  | Product Data
Toilet, Bath, and Laundry Accessories_Mirror Unit | Yes | 102800 | 2.2-H |  | Product Data
Toilet, Bath, and Laundry Accessories_Hook | Yes | 102800 | 2.2-J |  | Product Data
Toilet, Bath, and Laundry Accessories_Shower Curtain | Yes | 102800 | 2.3-B |  | Product Data
Toilet, Bath, and Laundry Accessories_Robe Hook | Yes | 102800 | 2.3-C |  | Product Data
Toilet, Bath, and Laundry Accessories_Stainless Steel | Yes | 102800 | 2.4-A |  | Product Data
Toilet, Bath, and Laundry Accessories_Galvanized-Steel Mounting Devices | Yes | 102800 | 2.4-B |  | Product Data
Toilet, Bath, and Laundry Accessories_Fasteners | Yes | 102800 | 2.4-C |  | Product Data
Fire Protection Cabinets_Fire Protection Cabinets | Yes | 104413 | 1.4-B |  | Shop Drawings
Fire Protection Cabinets_Exposed Finish | Yes | 104413 | 1.4-C |  | Sample
Fire Protection Cabinets_Product Schedule | Yes | 104413 | 1.4-F |  | Schedule
Fire Protection Cabinets_Recessed Cabinet Trimless with Hidden Flange | Yes | 104413 | 2.3-D-1 |  | Product Data
Fire Protection Cabinets_Recessed Cabiner Accessories | Yes | 104413 | 2.3-D-1 |  | Product Data
Fire Protection Cabinets_Tempered Float Glass | Yes | 104413 | 2.3-E-2 |  | Product Data
Fire Extinguishers_Product Schedule | Yes | 104416 | 1.4-B |  | Schedule
Fire Extinguishers_Warranty_Informational | Yes | 104416 | 1.5-A |  | Warranty
Fire Extinguishers_Multipurpose Dry-Chemical Fire Extinguisher In Aluminum Container | Yes | 104416 | 2.2-A |  | Product Data
Fire Extinguishers_Carbon Dioxide Fire Extinguisher | Yes | 104416 | 2.2-B |  | Product Data
Plastic-Laminate-Clad Lockers_Plastic-Laminate-Clad Wood Lockers | Yes | 105123 | 1.3-B |  | Shop Drawings
Plastic-Laminate-Clad Lockers_High-Pressure Decorative Laminates | Yes | 105123 | 1.3-C-1 |  | Sample
Plastic-Laminate-Clad Lockers_Thermoset Decorative Overlay Panels | Yes | 105123 | 1.3-C-2 |  | Sample
Plastic-Laminate-Clad Lockers_Carpet | Yes | 105123 | 1.3-C-3 |  | Sample
Plastic-Laminate-Clad Lockers_Plastic-Laminate-Clad Panels | Yes | 105123 | 1.3-D-1 |  | Sample
Plastic-Laminate-Clad Lockers_Corner Pieces Of Locker Front Frame Joints | Yes | 105123 | 1.3-D-3 |  | Sample
Plastic-Laminate-Clad Lockers_Exposed Cabinet Hardware and Accessories | Yes | 105123 | 1.3-D-4 |  | Sample
Plastic-Laminate-Clad Lockers_Installer_Informational | Yes | 105123 | 1.4-A |  | Qualifications
Plastic-Laminate-Clad Lockers_Sample Warranty_Informational | Yes | 105123 | 1.4-B |  | Warranty
Plastic-Laminate-Clad Lockers_Plastic-Laminate-Clad Wood Lockers | Yes | 105123 | 2.2 |  | Product Data
Plastic-Laminate-Clad Lockers_Composite Wood | Yes | 105123 | 2.3-A |  | Product Data
Plastic-Laminate-Clad Lockers_High-Pressure Decorative Laminate | Yes | 105123 | 2.3-B |  | Product Data
Plastic-Laminate-Clad Lockers_Furring, Blocking, Shims, and Hanging Strips | Yes | 105123 | 2.3-C |  | Product Data
Plastic-Laminate-Clad Lockers_Anchors | Yes | 105123 | 2.3-D |  | Product Data
Plastic-Laminate-Clad Lockers_Wood Support Base | Yes | 105123 | 2.3-E |  | Product Data
Plastic-Laminate-Clad Lockers_Built-In Combination Lock | Yes | 105123 | 2.4-A |  | Product Data
Plastic-Laminate-Clad Lockers_Frameless Hinges (European Type) | Yes | 105123 | 2.4-B |  | Product Data
Plastic-Laminate-Clad Lockers_Wire Pulls | Yes | 105123 | 2.4-C |  | Product Data
Plastic-Laminate-Clad Lockers_Accessible Handle | Yes | 105123 | 2.4-D |  | Product Data
Plastic-Laminate-Clad Lockers_Shelf Rests | Yes | 105123 | 2.4-E |  | Product Data
Plastic-Laminate-Clad Lockers_Hooks | Yes | 105123 | 2.4-F |  | Product Data
Plastic-Laminate-Clad Lockers_Coat Rods | Yes | 105123 | 2.4-G |  | Product Data
Plastic-Laminate-Clad Lockers_Exposed Hardware Finish | Yes | 105123 | 2.4-H |  | Product Data
Plastic-Laminate-Clad Lockers_Protective Mats | Yes | 105123 | 2.5-A |  | Product Data
Plastic-Laminate-Clad Lockers_Number Identification Plates | Yes | 105123 | 2.5-B |  | Product Data
Loading Dock Seals and Shelters_Loading Dock Seals and Shelters | Yes | 111316 | 1.4-B |  | Shop Drawings
Loading Dock Seals and Shelters_Fabric | Yes | 111316 | 1.4-C |  | Sample
Loading Dock Seals and Shelters_Foam-Pad Loading Dock Seals | Yes | 111316 | 2.2 |  | Product Data
Loading Dock Seals and Shelters_Vinyl-Coated Nylon Cover Fabric | Yes | 111316 | 2.2-E-1 |  | Product Data
Loading Dock Seals and Shelters_Cover Fabric | Yes | 111316 | 2.2-E-2 |  | Product Data
Loading Dock Seals and Shelters_Pleated Protectors | Yes | 111316 | 2.2-E-3 |  | Product Data
Loading Dock Seals and Shelters_Wood | Yes | 111316 | 2.2-E-4 |  | Product Data
Loading Dock Seals and Shelters_Pressure-Treated Wood | Yes | 111316 | 2.2-E-5 |  | Product Data
Stationary Loading Dock Equipment_Stationary Loading Dock Equipment | Yes | 111319 | 1.6-B |  | Shop Drawings
Stationary Loading Dock Equipment_Installer_Informational | Yes | 111319 | 1.7-A |  | Qualifications
Stationary Loading Dock Equipment_Welding Certificates_Informational | Yes | 111319 | 1.7-B |  | Certificate
Stationary Loading Dock Equipment_Product Test Reports_Informational | Yes | 111319 | 1.7-C |  | Report
Stationary Loading Dock Equipment_Sample Warranty_Informational | Yes | 111319 | 1.7-D |  | Warranty
Stationary Loading Dock Equipment_Recessed Loading Dock Levelers | Yes | 111319 | 2.1 |  | Product Data
Stationary Loading Dock Equipment_Light Communication Systems | Yes | 111319 | 2.2 |  | Product Data
Laboratory Fume Hoods_Laboratory Fume Hoods | Yes | 115313 | 1.4-B |  | Shop Drawings
Laboratory Fume Hoods_Seismic Performance and Design Criteria Delegated-Design Submittal | Yes | 115313 | 1.4-C |  | Report
Laboratory Fume Hoods_Product Test Reports_Informational | Yes | 115313 | 1.5-A |  | Report
Laboratory Fume Hoods_Source Quality-Control Reports_Informational | Yes | 115313 | 1.5-B |  | Report
Laboratory Fume Hoods_Field Quality-Control Reports_Informational | Yes | 115313 | 1.5-C |  | Report
Laboratory Fume Hoods_Fume Hoods | Yes | 115313 | 2.3 |  | Product Data
Laboratory Fume Hoods_Steel Sheet | Yes | 115313 | 2.4-A |  | Product Data
Laboratory Fume Hoods_Epoxy | Yes | 115313 | 2.4-C |  | Product Data
Laboratory Fume Hoods_Polypropylene | Yes | 115313 | 2.4-D |  | Product Data
Laboratory Fume Hoods_Electrical Components, Devices, and Accessories | Yes | 115313 | 2.4-F |  | Product Data
Laboratory Fume Hoods_Fasteners | Yes | 115313 | 2.4-G |  | Product Data
Laboratory Fume Hoods_Fume Hood Base Cabinets, Work Tops and Service Fittings | Yes | 115313 | 2.6 |  | Product Data
Laboratory Fume Hoods_Airflow Indicator and Alarm | Yes | 115313 | 2.8-A |  | Product Data
Laboratory Fume Hoods_Airflow Indicator | Yes | 115313 | 2.8-B |  | Product Data
Laboratory Fume Hoods_Sash Alarm | Yes | 115313 | 2.8-C |  | Product Data
Laboratory Fume Hoods_Sash Stops | Yes | 115313 | 2.8-D |  | Product Data
Laboratory Fume Hoods_Bypass Grille Blank-Off Panel | Yes | 115313 | 2.8-E |  | Product Data
Laboratory Fume Hoods_Automatic Sash Operator | Yes | 115313 | 2.8-F |  | Product Data
Facility Waste Compactors_Each Waste Compactor And For Special Components | Yes | 118226 | 1.4-B |  | Shop Drawings
Facility Waste Compactors_Installer_Informational | Yes | 118226 | 1.5-A |  | Qualifications
Facility Waste Compactors_Waste Compactor_Informational | Yes | 118226 | 1.5-B |  | Certificate
Facility Waste Compactors_Field Quality-Control Reports_Informational | Yes | 118226 | 1.5-C |  | Report
Facility Waste Compactors_Facility Waste Compactors | Yes | 118226 | 2.1 |  | Product Data
Roller Window Shades_Motor-Operated Shades | Yes | 122413 | 1.3-B-1 |  | Shop Drawings
Roller Window Shades_Each Exposed Product And Color And Texture | Yes | 122413 | 1.3-C |  | Sample
Roller Window Shades_Shadeband Material | Yes | 122413 | 1.3-D-1 |  | Sample
Roller Window Shades_Roller Shade | Yes | 122413 | 1.3-D-2 |  | Sample
Roller Window Shades_Installation Accessories | Yes | 122413 | 1.3-D-3 |  | Sample
Roller Window Shades_Installer_Informational | Yes | 122413 | 1.4-A |  | Qualifications
Roller Window Shades_Shadeband Material_Informational | Yes | 122413 | 1.4-B |  | Certificate
Roller Window Shades_Shadeband Material_Informational | Yes | 122413 | 1.4-C |  | Report
Roller Window Shades_Bead Chains | Yes | 122413 | 2.2-B-1 |  | Product Data
Roller Window Shades_Spring Lift-Assist Mechanisms | Yes | 122413 | 2.2-B-2 |  | Product Data
Roller Window Shades_Rollers | Yes | 122413 | 2.2-C |  | Product Data
Roller Window Shades_Mounting Hardware | Yes | 122413 | 2.2-D |  | Product Data
Roller Window Shades_Roller-Coupling Assemblies | Yes | 122413 | 2.2-E |  | Product Data
Roller Window Shades_Shadebands | Yes | 122413 | 2.2-F |  | Product Data
Roller Window Shades_Front Fascia | Yes | 122413 | 2.2-G-1 |  | Product Data
Roller Window Shades_Exposed Headbox | Yes | 122413 | 2.2-G-2 |  | Product Data
Roller Window Shades_Endcap Covers | Yes | 122413 | 2.2-G-3 |  | Product Data
Roller Window Shades_Closure Panel And Wall Clip | Yes | 122413 | 2.2-G-4 |  | Product Data
Roller Window Shades_Side Channels | Yes | 122413 | 2.2-G-5 |  | Product Data
Roller Window Shades_Bottom (Sill) Channel Or Angle | Yes | 122413 | 2.2-G-6 |  | Product Data
Roller Window Shades_Light-Filtering Fabric | Yes | 122413 | 2.3-B |  | Product Data
Metal Laboratory Casework_Laboratory Casework | Yes | 123553.13 | 1.5-B |  | Shop Drawings
Metal Laboratory Casework_Keying Schedule | Yes | 123553.13 | 1.5-C |  | Schedule
Metal Laboratory Casework_Casework Finishes And Casework Materials | Yes | 123553.13 | 1.5-D |  | Sample
Metal Laboratory Casework_Each Type Of Casework, Exposed-Hardware And Countertop-Material Finish | Yes | 123553.13 | 1.5-F |  | Sample
Metal Laboratory Casework_Delegated-Design Submittal | Yes | 123553.13 | 1.5-G |  | Leed Requirements
Metal Laboratory Casework_Manufacturer_Informational | Yes | 123553.13 | 1.6-A |  | Qualifications
Metal Laboratory Casework_Casework_Informational | Yes | 123553.13 | 1.6-B-1 |  | Report
Metal Laboratory Casework_Countertop Surface Material_Informational | Yes | 123553.13 | 1.6-B-2 |  | Report
Metal Laboratory Casework_Flammable Liquid Storage | Yes | 123553.13 | 2.3-B |  | Product Data
Metal Laboratory Casework_Electrical Components, Devices, And Accessories | Yes | 123553.13 | 2.3-C |  | Product Data
Metal Laboratory Casework_Metal Casework Material - Steel Sheet | Yes | 123553.13 | 2.4-A |  | Product Data
Metal Laboratory Casework_Acid Storage-Cabinet Lining | Yes | 123553.13 | 2.5-A |  | Product Data
Metal Laboratory Casework_Cabinet Hardware - Hinges | Yes | 123553.13 | 2.6-B |  | Product Data
Metal Laboratory Casework_Cabinet Hardware - Hinged-Door And Drawer Pulls | Yes | 123553.13 | 2.6-C |  | Product Data
Metal Laboratory Casework_Cabinet Hardware - Sliding-Door Pulls | Yes | 123553.13 | 2.6-D |  | Product Data
Metal Laboratory Casework_Cabinet Hardware - Channel Pulls | Yes | 123553.13 | 2.6-E |  | Product Data
Metal Laboratory Casework_Cabinet Hardware - Door Catches | Yes | 123553.13 | 2.6-F |  | Product Data
Metal Laboratory Casework_Cabinet Hardware - Drawer Slides | Yes | 123553.13 | 2.6-G |  | Product Data
Metal Laboratory Casework_Cabinet Hardware - Label Holders | Yes | 123553.13 | 2.6-H |  | Product Data
Metal Laboratory Casework_Cabinet Hardware - Locks | Yes | 123553.13 | 2.6-I |  | Product Data
Metal Laboratory Casework_Cabinet Hardware - Sliding-Door Hardware Sets | Yes | 123553.13 | 2.6-J |  | Product Data
Metal Laboratory Casework_Countertop Tabletop, Shelf And Sink Material | Yes | 123553.13 | 2.7 |  | Product Data
Metal Laboratory Casework_Metal Cabints And Tables - Flush Doors | Yes | 123553.13 | 2.8-B |  | Product Data
Metal Laboratory Casework_Metal Cabints And Tables - Glazed Doors | Yes | 123553.13 | 2.8-C |  | Product Data
Metal Laboratory Casework_Metal Cabints And Tables - Hinged Doors | Yes | 123553.13 | 2.8-D |  | Product Data
Metal Laboratory Casework_Metal Cabints And Tables - Drawers | Yes | 123553.13 | 2.8-E |  | Product Data
Metal Laboratory Casework_Metal Cabints And Tables - Adjustable Shelves | Yes | 123553.13 | 2.8-F |  | Product Data
Metal Laboratory Casework_Metal Cabints And Tables - Toe Space | Yes | 123553.13 | 2.8-G |  | Product Data
Metal Laboratory Casework_Metal Cabints And Tables - Tables | Yes | 123553.13 | 2.8-H |  | Product Data
Metal Laboratory Casework_Metal Cabints And Tables - Utilities | Yes | 123553.13 | 2.8-I |  | Product Data
Metal Laboratory Casework_Metal Cabints And Tables - Utility-Space Framing | Yes | 123553.13 | 2.8-J |  | Product Data
Metal Laboratory Casework_Metal Cabints And Tables - Filler And Closure Panels | Yes | 123553.13 | 2.8-K |  | Product Data
Metal Laboratory Casework_Laboratory Casework System - Support Framing | Yes | 123553.13 | 2.9-B |  | Product Data
Metal Laboratory Casework_Laboratory Casework System - Undercabinet Task-Light Luminaires | Yes | 123553.13 | 2.9-C |  | Product Data
Metal Laboratory Casework_Laboratory Casework System - Countertops | Yes | 123553.13 | 2.9-C |  | Product Data
Metal Laboratory Casework_Metal Cabinet Finish - Chemical-Resistant Finish | Yes | 123553.13 | 2.10-C |  | Product Data
Metal Laboratory Casework_Countertops, Tabletops, Shelves And Sinks - Countertops | Yes | 123553.13 | 2.11-A |  | Product Data
Metal Laboratory Casework_Laboratory Casework System - Outlets | Yes | 123553.13 | 2.11-B-1 |  | Product Data
Metal Laboratory Casework_Laboratory Casework System - Overflows | Yes | 123553.13 | 2.11-B-2 |  | Product Data
Metal Laboratory Casework_Laboratory Casework System - Epoxy Countertops And Sinks | Yes | 123553.13 | 2.11-C |  | Product Data
Metal Laboratory Casework_Laboratory Casework System - Stainless Steel Shelves | Yes | 123553.13 | 2.11-D |  | Product Data
Metal Laboratory Casework_Laboratory Accessories - Reagent Shelves | Yes | 123553.13 | 2.12-A |  | Product Data
Metal Laboratory Casework_Laboratory Accessories - Burette Rods | Yes | 123553.13 | 2.12-B |  | Product Data
Metal Laboratory Casework_Laboratory Accessories - Upright Rod Assembly And Metal Crossbar | Yes | 123553.13 | 2.12-C |  | Product Data
Metal Laboratory Casework_Laboratory Accessories - Greenlaw Arm Assembly | Yes | 123553.13 | 2.12-D |  | Product Data
Metal Laboratory Casework_Laboratory Accessories - Plastic Or Resin Pegboards | Yes | 123553.13 | 2.12-E |  | Product Data
Metal Laboratory Casework_Water And Laboratory Gas Service Fittings - Service Fittings | Yes | 123553.13 | 2.13-B |  | Product Data
Metal Laboratory Casework_Water And Laboratory Gas Service Fittings - Reagent-Grade Water Service Fittings | Yes | 123553.13 | 2.13-B |  | Product Data
Metal Laboratory Casework_Water And Laboratory Gas Service Fittings - Water Valves And Faucets | Yes | 123553.13 | 2.13-E |  | Product Data
Metal Laboratory Casework_Water And Laboratory Gas Service Fittings - Ground-Key Cocks | Yes | 123553.13 | 2.13-F |  | Product Data
Metal Laboratory Casework_Water And Laboratory Gas Service Fittings - Hand Of Fittings | Yes | 123553.13 | 2.13-G |  | Product Data
Metal Laboratory Casework_Water And Laboratory Gas Service Fittings - Handles | Yes | 123553.13 | 2.13-H |  | Product Data
Metal Laboratory Casework_Water And Laboratory Gas Service Fittings - Service-Outlet Identification | Yes | 123553.13 | 2.13-I |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Service Fittings | Yes | 123553.13 | 2.14-A |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Electrical Wiring Devices | Yes | 123553.13 | 2.14-B |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Isolated-Ground, Duplex Convenience Receptacles | Yes | 123553.13 | 2.14-C-1 |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Duplex GFCI Convenience Receptacles | Yes | 123553.13 | 2.14-C-2 |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Single-Pole Switches | Yes | 123553.13 | 2.14-D-1 |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Two-Pole Switches | Yes | 123553.13 | 2.14-D-2 |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Pilot-Light Switches, Single Pole | Yes | 123553.13 | 2.14-D-3 |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Key-Operated Switches | Yes | 123553.13 | 2.14-D-4 |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Data Communication Outlets | Yes | 123553.13 | 2.14-E |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Cover Plates | Yes | 123553.13 | 2.14-F |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Cover Plate Identification | Yes | 123553.13 | 2.14-G |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Pedestal-Type Fittings | Yes | 123553.13 | 2.14-H |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Line-Type Fittings | Yes | 123553.13 | 2.14-I |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Recessed-Type Fittings | Yes | 123553.13 | 2.14-J |  | Product Data
Metal Laboratory Casework_Electrical And Communication Service Fittings - Finishes For Service-Fitting Components | Yes | 123553.13 | 2.14-K |  | Product Data
Plastic-Laminate-Clad Countertops_Plastic-Laminate-Clad Countertops | Yes | 123623.13 | 1.3-B |  | Shop Drawings
Plastic-Laminate-Clad Countertops_Plastic Laminates | Yes | 123623.13 | 1.3-C |  | Sample
Plastic-Laminate-Clad Countertops_Plastic Laminates | Yes | 123623.13 | 1.3-D |  | Sample
Plastic-Laminate-Clad Countertops_Plastic Laminates | Yes | 123623.13 | 1.3-E-1 |  | Sample
Plastic-Laminate-Clad Countertops_Fabrication Samples | Yes | 123623.13 | 1.3-E-2 |  | Sample
Plastic-Laminate-Clad Countertops_Installer_Informational | Yes | 123623.13 | 1.4-A |  | Qualifications
Plastic-Laminate-Clad Countertops_Composite Wood And Agrifiber Products_Informational | Yes | 123623.13 | 1.4-B-1 |  | Certificate
Plastic-Laminate-Clad Countertops_High-Pressure Decorative Laminate _Informational | Yes | 123623.13 | 1.4-B-2 |  | Certificate
Plastic-Laminate-Clad Countertops_Chemical-Resistant, High-Pressure Decorative Laminate_Informational | Yes | 123623.13 | 1.4-B-3 |  | Certificate
Plastic-Laminate-Clad Countertops_Adhesives_Informational | Yes | 123623.13 | 1.4-B-4 |  | Certificate
Plastic-Laminate-Clad Countertops_Quality Standard Compliance Certificates_Informational | Yes | 123623.13 | 1.4-C |  | Certificate
Plastic-Laminate-Clad Countertops_Fire-Retardant-Treated Materials_Informational | Yes | 123623.13 | 1.4-C |  | Report
Plastic-Laminate-Clad Countertops_Plastic-Laminate-Clad Countertops | Yes | 123623.13 | 2.1 |  | Product Data
Plastic-Laminate-Clad Countertops_Composite Wood And Agrifiber Products | Yes | 123623.13 | 2.2-B |  | Product Data
Plastic-Laminate-Clad Countertops_Fire-Retardant-Treated Materials, | Yes | 123623.13 | 2.3-A |  | Product Data
Plastic-Laminate-Clad Countertops_Fire-Retardant Particleboard | Yes | 123623.13 | 2.3-B |  | Product Data
Plastic-Laminate-Clad Countertops_Fire-Retardant Mdf | Yes | 123623.13 | 2.3-C |  | Product Data
Plastic-Laminate-Clad Countertops_Wire-Management Grommets | Yes | 123623.13 | 2.4-A |  | Product Data
Plastic-Laminate-Clad Countertops_Adhesive For Bonding Plastic Laminate | Yes | 123623.13 | 2.5-A |  | Product Data
Solid Surfacing Countertops_Countertops | Yes | 123661.16 | 1.3-B |  | Shop Drawings
Solid Surfacing Countertops_Each Type Of Material Exposed To View | Yes | 123661.16 | 1.3-C |  | Sample
Solid Surfacing Countertops_Countertop Material | Yes | 123661.16 | 1.3-D-1 |  | Sample
Solid Surfacing Countertops_Wood Trim | Yes | 123661.16 | 1.3-D-2 |  | Sample
Solid Surfacing Countertops_Solid Surface Material Countertop | Yes | 123661.16 | 1.3-D-3 |  | Sample
Solid Surfacing Countertops_Fabricator_Informational | Yes | 123661.16 | 1.4-A |  | Qualifications
Solid Surfacing Countertops_Solid Surface Countertop Materials - Solid Surface Material | Yes | 123661.16 | 2.1-A |  | Product Data
Solid Surfacing Countertops_Solid Surface Countertop Materials - Solid Wood Edges And Trim | Yes | 123661.16 | 2.1-B |  | Product Data
Solid Surfacing Countertops_Solid Surface Countertop Materials - Particleboard | Yes | 123661.16 | 2.1-C |  | Product Data
Solid Surfacing Countertops_Solid Surface Countertop Materials - Plywood | Yes | 123661.16 | 2.1-D |  | Product Data
Solid Surfacing Countertops_Countertop Fabrication - Countertops | Yes | 123661.16 | 2.2-C |  | Product Data
Solid Surfacing Countertops_Countertop Fabrication - Backsplashes | Yes | 123661.16 | 2.2-D |  | Product Data
Solid Surfacing Countertops_Countertop Fabrication - Joints | Yes | 123661.16 | 2.2-F |  | Product Data
Solid Surfacing Countertops_Countertop Fabrication - Undercounter Plumbing Fixtures | Yes | 123661.16 | 2.2-H-1 |  | Product Data
Solid Surfacing Countertops_Countertop Fabrication - Counter-Mounted Plumbing Fixtures | Yes | 123661.16 | 2.2-H-2 |  | Product Data
Solid Surfacing Countertops_Countertop Fabrication - Fittings | Yes | 123661.16 | 2.2-H-3 |  | Product Data
Solid Surfacing Countertops_Countertop Fabrication - Counter-Mounted Cooktops | Yes | 123661.16 | 2.2-H-4 |  | Product Data
Solid Surfacing Countertops_Installation Materials - Adhesives | Yes | 123661.16 | 2.3-A |  | Product Data
Solid Surfacing Countertops_Installation Materials - Sealants For Countertops | Yes | 123661.16 | 2.3-B |  | Product Data
Compressed Air Equipment_Data Sheets | Yes | 220481 | 1.3 |  | Report
Compressed Air Equipment_Air Compressors - Compressors | Yes | 220481 | 2.1 |  | Product Data
Compressed Air Equipment_Air Compressors - Enclosure And Frame | Yes | 220481 | 2.1 |  | Product Data
Compressed Air Equipment_Air Compressors - Air Compressor Control Panel | Yes | 220481 | 2.1 |  | Product Data
Compressed Air Equipment_Air Compressors - Safety Devices | Yes | 220481 | 2.1 |  | Product Data
Compressed Air Equipment_Air Compressors - Motor Control | Yes | 220481 | 2.1 |  | Product Data
Compressed Air Equipment_Compressed Air Receivers | Yes | 220481 | 2.2 |  | Product Data
Compressed Air Equipment_Compressed Air Dryers - Refrigerant Air Dryers | Yes | 220481 | 2.3 |  | Product Data
Compressed Air System Specialities_Pneumatic Drain Traps | Yes | 220482 | 2.1 |  | Product Data
Compressed Air System Specialities_Flexible Connectors | Yes | 220482 | 2.2 |  | Product Data
Compressed Air System Specialities_Regulators In Copper Lines | Yes | 220482 | 2.3 |  | Product Data
Compressed Air System Specialities_Regulators In Stainless Steel Lines | Yes | 220482 | 2.3 |  | Product Data
Compressed Air System Specialities_Regulators (Precision) | Yes | 220482 | 2.3 |  | Product Data
Compressed Air System Specialities_Pressure Safety Valves | Yes | 220482 | 2.4 |  | Product Data
Compressed Air System Specialities_Wall Gas Outlet Escutcheons | Yes | 220482 | 2.5 |  | Product Data
Compressed Air System Specialities_Quick-Connect Outlet Conmections | Yes | 220482 | 2.6 |  | Product Data
Compressed Air System Specialities_Bleed Valves | Yes | 220482 | 2.7 |  | Product Data
Compressed Air System Specialities_Tube And Adapter Fittings | Yes | 220482 | 2.8 |  | Product Data
Compressed Air System Specialities_Membrane Point Of Use Dessicant Dryer | Yes | 220482 | 2.9 |  | Product Data
Basic Mechanical Requirements_Mechanical Requirements | Yes | 230010 | 1.5.2 |  | Shop Drawings
Basic Mechanical Requirements_Mechanical Requirements | Yes | 230010 | 1.5.3 |  | Record Drawing
Basic Mechanical Requirements_Mechanical Requirements | Yes | 230010 | 1.5 |  | Product Data
Controlled Environmental Chamber_Design Loads | Yes | 230038 | 1.2 |  | Calculations
Controlled Environmental Chamber_Controlled Environment Room | Yes | 230038 | 1.2 |  | Shop Drawings
Controlled Environmental Chamber_Single-Line Diagrams | Yes | 230038 | 1.2 |  | Shop Drawings
Controlled Environmental Chamber_Schematic Diagrams | Yes | 230038 | 1.2 |  | Shop Drawings
Controlled Environmental Chamber_Wiring Diagrams | Yes | 230038 | 1.2 |  | Shop Drawings
Controlled Environmental Chamber_Wall And Ceiling Panels | Yes | 230038 | 2.3 |  | Product Data
Controlled Environmental Chamber_Entrance Door (Swing Doors) | Yes | 230038 | 2.4 |  | Product Data
Controlled Environmental Chamber_Entrance Door (Powered Horizontal Sliding Doors) | Yes | 230038 | 2.5 |  | Product Data
Controlled Environmental Chamber_Observation Windows In Wall Panels Or Entrance Door | Yes | 230038 | 2.6 |  | Product Data
Controlled Environmental Chamber_Pressure Relief Port | Yes | 230038 | 2.7 |  | Product Data
Controlled Environmental Chamber_Chamber Size | Yes | 230038 | 2.8 |  | Product Data
Controlled Environmental Chamber_Shelving | Yes | 230038 | 2.10 |  | Product Data
Controlled Environmental Chamber_Casework | Yes | 230038 | 2.10 |  | Product Data
Controlled Environmental Chamber_Floor Mat | Yes | 230038 | 2.10 |  | Product Data
Controlled Environmental Chamber_Wall Bumper Rails | Yes | 230038 | 2.10 |  | Product Data
Controlled Environmental Chamber_Corner Guards | Yes | 230038 | 2.10 |  | Product Data
Controlled Environmental Chamber_Receptacles | Yes | 230038 | 2.11 |  | Product Data
Controlled Environmental Chamber_Raceway | Yes | 230038 | 2.11 |  | Product Data
Controlled Environmental Chamber_Wiring | Yes | 230038 | 2.11 |  | Product Data
Controlled Environmental Chamber_Chambers (Low Height) | Yes | 230038 | 2.12 |  | Product Data
Controlled Environmental Chamber_Light Levels (Storage Chambers) | Yes | 230038 | 2.12 |  | Product Data
Controlled Environmental Chamber_Sleeves/Passthrough Ports | Yes | 230038 | 2.13 |  | Product Data
Controlled Environmental Chamber_Controls | Yes | 230038 | 2.14 |  | Product Data
Controlled Environmental Chamber_Refrigeration Equipment | Yes | 230038 | 2.15 |  | Product Data
Basic Mechanical Materials And Methods_Mildew-Resistant Silicone Sealants | Yes | 230050 | 2.3 |  | Product Data
Basic Mechanical Materials And Methods_Penetration Firestopping Systems | Yes | 230050 | 2.3 |  | Product Data
Basic Mechanical Materials And Methods_Grout | Yes | 230050 | 2.4 |  | Product Data
Hangers Ans Supports_Pipe Hanger Assembly | Yes | 230140 | 1.5 |  | Shop Drawings
Hangers Ans Supports_Equipment Support | Yes | 230140 | 1.5 |  | Shop Drawings
Hangers Ans Supports_Non-Sanitary System Piping Supports | Yes | 230140 | 2.1 |  | Product Data
Hangers Ans Supports_Carbon-Steel Pipe Hangers And Supports | Yes | 230140 | 2.2 |  | Product Data
Hangers Ans Supports_Stainless-Steel Pipe Hangers And Supports | Yes | 230140 | 2.2 |  | Product Data
Hangers Ans Supports_Copper Pipe Hangers | Yes | 230140 | 2.2 |  | Product Data
Hangers Ans Supports_Trapeze Pipe Hangers | Yes | 230140 | 2.3 |  | Product Data
Hangers Ans Supports_Metal Strut Systems | Yes | 230140 | 2.4 |  | Product Data
Hangers Ans Supports_Insulation Insert Material For Hot Piping | Yes | 230140 | 2.5 |  | Product Data
Hangers Ans Supports_Insulation Insert Material For Cold Piping | Yes | 230140 | 2.5 |  | Product Data
Hangers Ans Supports_Powder-Actuated Fasteners | Yes | 230140 | 2.6 |  | Product Data
Hangers Ans Supports_Mechanical-Expansion Anchors | Yes | 230140 | 2.6 |  | Product Data
Hangers Ans Supports_Compact Pipe Stand | Yes | 230140 | 2.7 |  | Product Data
Hangers Ans Supports_High-Type, Single-Pipe Stand | Yes | 230140 | 2.7 |  | Product Data
Hangers Ans Supports_High-Type, Multiple-Pipe Stand | Yes | 230140 | 2.7 |  | Product Data
Hangers Ans Supports_Curb-Mounted-Type Pipe Stands | Yes | 230140 | 2.7 |  | Product Data
Hangers Ans Supports_Heavy-Duty Steel Trapezes | Yes | 230140 | 2.8 |  | Product Data
Hangers Ans Supports_Roof Curbs | Yes | 230140 | 2.9 |  | Product Data
Hangers Ans Supports_Equipment Or Material Support Curbs | Yes | 230140 | 2.9 |  | Product Data
Hangers Ans Supports_Equipment Support Pads | Yes | 230140 | 2.10 |  | Product Data
Hydronic System Specialties_Flexible Connectors | Yes | 230510 | 2.2 |  | Product Data
Hydronic System Specialties_Flexible Connectors – Spherical Type | Yes | 230510 | 2.3 |  | Product Data
Hydronic System Specialties_Flexible Utility Hoses | Yes | 230510 | 2.4 |  | Product Data
Hydronic System Specialties_Calibrated Balancing Valves (Circuit Setters) | Yes | 230510 | 2.5.1 |  | Product Data
Hydronic System Specialties_Combination Manual Balancing Valve / Shut Off Valve | Yes | 230510 | 2.5.2 |  | Product Data
Hydronic System Specialties_Combined Pressure/Temperature Safety Valves | Yes | 230510 | 2.5.3 |  | Product Data
Hydronic System Specialties_Pressure Safety Valves | Yes | 230510 | 2.5.4 |  | Product Data
Hydronic System Specialties_Hydronic Specialties | Yes | 230510 | 2.6 |  | Product Data
Hydronic System Specialties_Cast Bronze Y-Strainers (1/2” – 2”) | Yes | 230510 | 2.6.1 |  | Product Data
Hydronic System Specialties_Cast Iron Y-Strainers (2-1/2” And Larger) | Yes | 230510 | 2.6.2 |  | Product Data
Hydronic System Specialties_Manual Air Vent | Yes | 230510 | 2.6.3 |  | Product Data
Hydronic System Specialties_Automatic Air Vent | Yes | 230510 | 2.6.4 |  | Product Data
Hydronic System Specialties_Diaphragm And Bladder-Type Expansion Tanks | Yes | 230510 | 2.6.5 |  | Product Data
Hydronic System Specialties_Air Separator | Yes | 230510 | 2.6.6 |  | Product Data
Hydronic System Specialties_Pump Suction Diffusers | Yes | 230510 | 2.6.7 |  | Product Data
Pumps_Pumps | Yes | 230540 | 1.4 |  | Shop Drawings
Pumps_Pumps | Yes | 230540 | 1.4 |  | Record Drawing
Pumps_Pumps | Yes | 230540 | 1.4.1 |  | MSDS
Pumps_Pumps | Yes | 230540 | 2.2 |  | Product Data
Pumps_Motors | Yes | 230540 | 2.3 |  | Product Data
Boilers_Boilers | Yes | 230555 | 1.1 |  | Shop Drawings
Boilers_Boilers | Yes | 230555 | 1.1 |  | Record Drawing
Boilers_Boilers | Yes | 230555 | 1.1 |  | Test Data
Boilers_Boilers | Yes | 230555 | 2.1 |  | Product Data
Breechings, Chimneys And Stacks_Certificates Of Materials Compliance | Yes | 230575 | 1.1 |  | Certificate
Breechings, Chimneys And Stacks_Welders' Qualification | Yes | 230575 | 1.1 |  | Qualifications
Breechings, Chimneys And Stacks_Design Wind And Seismic Loads | Yes | 230575 | 1.1 |  | Calculations
Chillers_Chillers | Yes | 230685 | 2.1 |  | Product Data
Chillers_Compressor | Yes | 230685 | 2.3 |  | Product Data
Chillers_Motor | Yes | 230685 | 2.4 |  | Product Data
Chillers_Variable Speed Drive | Yes | 230685 | 2.5 |  | Product Data
Chillers_Heat Exchangers | Yes | 230685 | 2.6 |  | Product Data
Chillers_Evaporator | Yes | 230685 | 2.7 |  | Product Data
Chillers_Condenser | Yes | 230685 | 2.8 |  | Product Data
Chillers_Refrigerant Flow Control | Yes | 230685 | 2.9 |  | Product Data
Chillers_Graphic Control Center | Yes | 230685 | 2.11 |  | Product Data
Chillers_Compressor Motor Starter Variable Speed Drive | Yes | 230685 | 2.12 |  | Product Data
Cooling Towers_Cooling Tower | Yes | 230711 | 2.1 |  | Product Data
Variable Flow Refrigerant System_Diagram Power, Signal, And Control Wiring | Yes | 230738 | 1.3 |  | Shop Drawings
Variable Flow Refrigerant System_ For Units With Factory-Applied Color Finishes | Yes | 230738 | 1.3 |  | Sample
Variable Flow Refrigerant System_Field Quality-Control Test Reports | Yes | 230738 | 1.3 |  | Report
Variable Flow Refrigerant System_Outdoor Units (Heat Pump), Air-Cooled Outdoor Units | Yes | 230738 | 2.2 |  | Product Data
Variable Flow Refrigerant System_Unit Cabinet | Yes | 230738 | 2.2.2 |  | Product Data
Variable Flow Refrigerant System_Fan | Yes | 230738 | 2.2.3 |  | Product Data
Variable Flow Refrigerant System_Refrigerant And Refrigerant Piping | Yes | 230738 | 2.2.4 |  | Product Data
Variable Flow Refrigerant System_Coil | Yes | 230738 | 2.2.5 |  | Product Data
Variable Flow Refrigerant System_Compressor | Yes | 230738 | 2.2.6 |  | Product Data
Variable Flow Refrigerant System_Controls | Yes | 230738 | 2.2.7 |  | Product Data
Variable Flow Refrigerant System_Electrical | Yes | 230738 | 2.2.8 |  | Product Data
Variable Flow Refrigerant System_Wall Mounted Indoor Unit | Yes | 230738 | 2.3 |  | Product Data
Variable Flow Refrigerant System_Filter | Yes | 230738 | 2.3.4 |  | Product Data
Air Coils_Air Coils | Yes | 230835 | 1.4 |  | Shop Drawings
Semi-Custom Air Handling Units _Semi-Custom Air Handling Units | Yes | 230855 | 2.1 |  | Product Data
Semi-Custom Air Handling Units _Base Rail | Yes | 230855 | 2.3.3 |  | Product Data
Semi-Custom Air Handling Units _Unit Casing | Yes | 230855 | 2.3.4 |  | Product Data
Semi-Custom Air Handling Units _Access Doors | Yes | 230855 | 2.3.5 |  | Product Data
Semi-Custom Air Handling Units _Vestibule | Yes | 230855 | 2.3.6 |  | Product Data
Semi-Custom Air Handling Units _Shafts And Hubs | Yes | 230855 | 2.4.2 |  | Product Data
Semi-Custom Air Handling Units _Bearings And Drive | Yes | 230855 | 2.4.3 |  | Product Data
Semi-Custom Air Handling Units _Hot Water Coils | Yes | 230855 | 2.5.2 |  | Product Data
Semi-Custom Air Handling Units _Cooling Water Coils | Yes | 230855 | 2.5.3 |  | Product Data
Semi-Custom Air Handling Units _ Primary Drain Pans | Yes | 230855 | 2.5.4 |  | Product Data
Semi-Custom Air Handling Units _Prefilters | Yes | 230855 | 2.11.2 |  | Product Data
Semi-Custom Air Handling Units _Main Filters | Yes | 230855 | 2.11.3 |  | Product Data
Semi-Custom Air Handling Units _Holding Frames For Prefilter And Main Filters | Yes | 230855 | 2.11.4 |  | Product Data
Semi-Custom Air Handling Units _Dampers | Yes | 230855 | 2.12 |  | Product Data
Semi-Custom Air Handling Units _Variable Frequency Drives | Yes | 230855 | 2.14.2 |  | Product Data
Semi-Custom Air Handling Units _Service Lighting And Outlets | Yes | 230855 | 2.14.3 |  | Product Data
Semi-Custom Air Handling Units _Motors | Yes | 230855 | 2.14.4 |  | Product Data
Air Rotation Unit_Air Rotation Unit | Yes | 230856 | 1.4 |  | Shop Drawings
Air Rotation Unit_Air Rotation Unit | Yes | 230856 | 1.4 |  | Record Drawing
Air Rotation Unit_Air Rotation Unit | Yes | 230856 | 1.4 |  | Product Data
Air Rotation Unit_Air Rotation Unit | Yes | 230856 | 1.4 |  | Schedule
Air Rotation Unit_Independent Fan Curves For Operating/Design Conditions | Yes | 230856 | 1.4 |  | Report
Air Rotation Unit_Coil Tube Fin And Casing | Yes | 230856 | 1.4 |  | Report
Air Rotation Unit_Installation Instructions | Yes | 230856 | 1.4 |  | Procedures
Air Rotation Unit_Utility Connections | Yes | 230856 | 1.4 |  | Shop Drawings
Air Rotation Unit_Air Rotation Units | Yes | 230856 | 2.1 |  | Product Data
Air Rotation Unit_Casing | Yes | 230856 | 2.3.2 |  | Product Data
Air Rotation Unit_Access Door | Yes | 230856 | 2.3.3 |  | Product Data
Air Rotation Unit_Electrical And Controls | Yes | 230856 | 2.4 |  | Product Data
Air Rotation Unit_Variable Frequency Drives | Yes | 230856 | 2.4.3 |  | Product Data
Air Rotation Unit_Service Lighting Ad Outlets | Yes | 230856 | 2.4.4 |  | Product Data
Air Rotation Unit_Supply Fans | Yes | 230856 | 2.5.1 |  | Product Data
Air Rotation Unit_Motors | Yes | 230856 | 2.5.2 |  | Product Data
Air Rotation Unit_Hot Water Coils | Yes | 230856 | 2.6.1 |  | Product Data
Air Rotation Unit_Chilled Water Coils | Yes | 230856 | 2.6.2 |  | Product Data
Air Rotation Unit_Filters | Yes | 230856 | 2.7 |  | Product Data
Air Rotation Unit_Prefilters | Yes | 230856 | 2.7.2 |  | Product Data
Air Rotation Unit_Main Filters | Yes | 230856 | 2.7.3 |  | Product Data
Air Rotation Unit_Holding Frames For Prefilter And Main Filters | Yes | 230856 | 2.7.4 |  | Product Data
Air Rotation Unit_Discharge Louvers | Yes | 230856 | 2.8 |  | Product Data
Air Rotation Unit_Accessories | Yes | 230856 | 2.9 |  | Product Data
Metal Ductwork_Sheet Metal Fabrication Drawings | Yes | 230891 | 1.5.1 |  | Shop Drawings
Metal Ductwork_Seam And Joint Construction | Yes | 230891 | 1.5.2 |  | Shop Drawings
Metal Ductwork_Sealing Materials | Yes | 230891 | 1.5.3 |  | Product Data
Metal Ductwork_Fire-Stopping Materials | Yes | 230891 | 1.5.4 |  | Product Data
Metal Ductwork_Hangers And Supports | Yes | 230891 | 1.5.5 |  | Product Data
Metal Ductwork_Duct Accessories | Yes | 230891 | 1.5.6 |  | Product Data
Metal Ductwork_Ductwork | Yes | 230891 | 1.5 |  | Record Drawing
Metal Ductwork_Rectangular Duct | Yes | 230891 | 2.2.1 |  | Product Data
Metal Ductwork_Flexible Ductwork | Yes | 230891 | 2.3 |  | Product Data
Metal Ductwork_Moisture Laden Exhaust Ductwork | Yes | 230891 | 2.4 |  | Product Data
Metal Ductwork_Miscellaneous Ductwork Materials | Yes | 230891 | 2.5 |  | Product Data
Metal Ductwork_Insulation | Yes | 230891 | 2.5 |  | Product Data
Metal Ductwork_Flanged Joint Tape | Yes | 230891 | 2.5 |  | Product Data
Metal Ductwork_Joint And Seam Sealant | Yes | 230891 | 2.5 |  | Product Data
Metal Ductwork_Duct Taping | Yes | 230891 | 2.5 |  | Product Data
Metal Ductwork_Ductwork Support Materials | Yes | 230891 | 2.5 |  | Product Data
Metal Ductwork_Fire Stopping | Yes | 230891 | 2.6 |  | Product Data
Ductwork Accessories_Ductwork Accessories | Yes | 230910 | 1.4 |  | Shop Drawings
Ductwork Accessories_Manual Volume Dampers, Rectangular (For Sizes 18”Wx10”H And Smaller) | Yes | 230910 | 2.2.2 |  | Product Data
Ductwork Accessories_Manual Volume Dampers, Round (For Sizes 12”Diameter And Smaller) | Yes | 230910 | 2.2.3 |  | Product Data
Ductwork Accessories_Manual Volume Dampers, Rectangular (For Sizes 18”Wx10”H And Larger) | Yes | 230910 | 2.2.4 |  | Product Data
Ductwork Accessories_Manual Volume Dampers, Round (For Sizes 12”Diameter To 24” Diameter) | Yes | 230910 | 2.2.5 |  | Product Data
Ductwork Accessories_Manual Volume Dampers, Rectangular (For Main Duct Medium Pressure And Velocities) | Yes | 230910 | 2.2.6 |  | Product Data
Ductwork Accessories_Manual Volume Dampers, Round (For Main Duct Medium Pressure And Velocities Up To 24" Diameter) | Yes | 230910 | 2.2.6 |  | Product Data
Ductwork Accessories_Bearing Seals | Yes | 230910 | 2.2.7 |  | Product Data
Ductwork Accessories_Remote Damper Operators | Yes | 230910 | 2.2.8 |  | Product Data
Ductwork Accessories_Rectangular Control Damper | Yes | 230910 | 2.2.9 |  | Product Data
Ductwork Accessories_Round Control Damper | Yes | 230910 | 2.2.10 |  | Product Data
Ductwork Accessories_Round Isolation Damper | Yes | 230910 | 2.2.11 |  | Product Data
Ductwork Accessories_Butterfly Backdraft Dampers | Yes | 230910 | 2.2.12 |  | Product Data
Ductwork Accessories_Backdraft Dampers (Rated At 4.0 To 10.0Inwg) | Yes | 230910 | 2.2.13 |  | Product Data
Ductwork Accessories_Fire And Smoke Dampers | Yes | 230910 | 2.3 |  | Product Data
Ductwork Accessories_One Hour And Two Hour Fire Dampers | Yes | 230910 | 2.3.1 |  | Product Data
Ductwork Accessories_Fire/Smoke Dampers | Yes | 230910 | 2.3.2 |  | Product Data
Ductwork Accessories_Turning Vanes | Yes | 230910 | 2.4 |  | Product Data
Ductwork Accessories_Duct Access Doors | Yes | 230910 | 2.5 |  | Product Data
Ductwork Accessories_Flexible Connections | Yes | 230910 | 2.6 |  | Product Data
Ductwork Accessories_Sound Attenuator | Yes | 230910 | 2.7 |  | Product Data
Air Outlets And Inlets_Air Outlets And Inlets | Yes | 230932 | 1.4 |  | Product Data
Air Outlets And Inlets_Radial Diffusers | Yes | 230932 | 2.1 |  | Product Data
Air Outlets And Inlets_Linear Diffusers | Yes | 230932 | 2.1 |  | Product Data
Air Outlets And Inlets_Nozzle Diffuser | Yes | 230932 | 2.1 |  | Product Data
Air Outlets And Inlets_Supply Grilles | Yes | 230932 | 2.1 |  | Product Data
Air Outlets And Inlets_Return Grilles | Yes | 230932 | 2.1 |  | Product Data
Air Outlets And Inlets_Supply Diffuser | Yes | 230932 | 2.1 |  | Product Data
Air Outlets And Inlets_Return Diffuser | Yes | 230932 | 2.1 |  | Product Data
Air Outlets And Inlets_Hepa Housing In Ductwork | Yes | 230932 | 2.2 |  | Product Data
Testing,Adjusting And Balancing_Contract Documents Examination Report | Yes | 230990 | 1.4 |  | Report
Testing,Adjusting And Balancing_Contractor | Yes | 230990 | 1.4 |  | Qualifications
Testing,Adjusting And Balancing_Strategies And Procedures Plan | Yes | 230990 | 1.4 |  | Procedures
Air Curtain_Diagram Power | Yes | 233433 | 1.3 |  | Shop Drawings
Air Curtain_Control Wiring | Yes | 233433 | 1.3 |  | Shop Drawings
Air Curtain_Signal | Yes | 233433 | 1.3 |  | Shop Drawings
Air Curtain_Field Quality-Control Test Reports | Yes | 233433 | 1.3 |  | Test Data
Air Curtain_Air Curtain | Yes | 233433 | 1.3 |  | Product Data
Air Curtain_Air Curtain | Yes | 233433 | 1.3 |  | Maintenance Data
Air Curtain_Materials & Components | Yes | 233433 | 2.1 |  | Product Data
Air Curtain_Hot Water Air Curtain | Yes | 233433 | 2.2 |  | Product Data
Air Curtain_Hot Water Coil | Yes | 233433 | 2.2 |  | Product Data
Air Curtain_Cabinet | Yes | 233433 | 2.2 |  | Product Data
Air Curtain_Unit | Yes | 233433 | 2.2 |  | Product Data
Basic Electrical Requirements_Coordination Drawings (As Per Submittal Schedule) | Yes | 260500 | 1.2 |  | Record Drawing
Basic Electrical Materials And Methods_Soil Materials | Yes | 260505 | 2.1 |  | Product Data
Basic Electrical Materials And Methods_Equipment Manufacturer's Nameplate Data | Yes | 260505 | 2.2 |  | Product Data
Basic Electrical Materials And Methods_Steel Plates, Shapes, Bars, And Bar Grating | Yes | 260505 | 2.3 |  | Product Data
Basic Electrical Materials And Methods_Cold-Formed Steel Tubing | Yes | 260505 | 2.3 |  | Product Data
Basic Electrical Materials And Methods_Hot-Rolled Steel Tubing | Yes | 260505 | 2.3 |  | Product Data
Basic Electrical Materials And Methods_Steel Pipe | Yes | 260505 | 2.3 |  | Product Data
Basic Electrical Materials And Methods_No Shrink, Nonmetallic Grou | Yes | 260505 | 2.3 |  | Product Data
Basic Electrical Materials And Methods_Fasteners | Yes | 260505 | 2.3 |  | Product Data
Basic Electrical Materials And Methods_Framing Materials | Yes | 260505 | 2.4 |  | Product Data
Basic Electrical Materials And Methods_Construction Panels | Yes | 260505 | 2.4 |  | Product Data
Basic Electrical Materials And Methods_Expanding Foam Sealants | Yes | 260505 | 2.5 |  | Product Data
Basic Electrical Materials And Methods_Mildew-Resistant Silicone Sealants | Yes | 260505 | 2.5 |  | Product Data
Basic Electrical Materials And Methods_Steel Access Doors And Frames | Yes | 260505 | 2.6 |  | Product Data
Basic Electrical Materials And Methods_Fire-Resistance Ratings | Yes | 260505 | 2.6 |  | Product Data
Basic Electrical Materials And Methods_Frames | Yes | 260505 | 2.6 |  | Product Data
Basic Electrical Materials And Methods_Gypsum Wallboard Or Plaster | Yes | 260505 | 2.6 |  | Product Data
Basic Electrical Materials And Methods_Full-Bed Plaster Applications | Yes | 260505 | 2.6 |  | Product Data
Basic Electrical Materials And Methods_Flush Panel Doors | Yes | 260505 | 2.6 |  | Product Data
Basic Electrical Materials And Methods_Fire-Rated Units | Yes | 260505 | 2.6 |  | Product Data
Basic Electrical Materials And Methods_Locking Devices | Yes | 260505 | 2.6 |  | Product Data
Basic Electrical Materials And Methods_Connectors And Terminals | Yes | 260505 | 2.7 |  | Product Data
Basic Electrical Materials And Methods_Raceway Supports | Yes | 260505 | 2.8 |  | Product Data
Basic Electrical Materials And Methods_Expansion Anchors | Yes | 260505 | 2.8 |  | Product Data
Basic Electrical Materials And Methods_Powder-Driven Threaded Studs | Yes | 260505 | 2.8 |  | Product Data
Basic Electrical Materials And Methods_Conduit Sealing Bushings | Yes | 260505 | 2.8 |  | Product Data
Basic Electrical Materials And Methods_Cable Supports For Vertical Conduit | Yes | 260505 | 2.8 |  | Product Data
Basic Electrical Materials And Methods_U-Channel Systems | Yes | 260505 | 2.8 |  | Product Data
Basic Electrical Materials And Methods_Lighting Fixture Supports | Yes | 260505 | 2.8 |  | Product Data
Basic Electrical Materials And Methods_Underground Line Marking Tape | Yes | 260505 | 2.9 |  | Product Data
Basic Electrical Materials And Methods_Wire/Cable Designation Tape Markers | Yes | 260505 | 2.9 |  | Product Data
Basic Electrical Materials And Methods_Junction Boxes And Outlet Boxes | Yes | 260505 | 2.9 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Conductors | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Interior (Dry Location) | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Interior (Wet Or Damp Location) | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Exterior (Roof And Above Grade) | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Jackets | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Aboveground Service-Entrance Cable | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Underground Service-Entrance Cable | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Multiconductor Flexible Cords | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Multiconductor Flexible Cords (Wet Location) | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Multiconductor Flexible Cords (Hazardous Location) | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Cable Tray | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Fire-Rated Cable | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Variable-Frequency Drive Cable | Yes | 260519 | 2.2 |  | Product Data
Low Voltage Electrical Power Conductors And Cables _Connectors For Conductors | Yes | 260519 | 2.3 |  | Product Data
Control Voltage Electrical Power Cables_Class 1 Control Circuits Stranded Copper | Yes | 260523 | 2.2 |  | Product Data
Control Voltage Electrical Power Cables_Class 2 Control Circuits Stranded Copper | Yes | 260523 | 2.2 |  | Product Data
Control Voltage Electrical Power Cables_Class 3 Remote-Control And Signal Circuits Stranded Copper | Yes | 260523 | 2.2 |  | Product Data
Control Voltage Electrical Power Cables_Paired Cable | Yes | 260523 | 2.2 |  | Product Data
Control Voltage Electrical Power Cables_Plenum-Rated, Paired Cable | Yes | 260523 | 2.2 |  | Product Data
Control Voltage Electrical Power Cables_UTP Cable | Yes | 260523 | 2.3 |  | Product Data
Control Voltage Electrical Power Cables_RS-485 Cable_General Cable | Yes | 260523 | 2.4 |  | Product Data
Control Voltage Electrical Power Cables_RS-485 Cable_Plenum-Rated Cable | Yes | 260523 | 2.4 |  | Product Data
Control Voltage Electrical Power Cables_RS-485 Cable_Plenum-Rated Cable In Cable Tray | Yes | 260523 | 2.4 |  | Product Data
Radiant Heating Electric Cables And Controls_For Each Heating Cable | Yes | 260524 | 1.5 |  | Shop Drawings
Radiant Heating Electric Cables And Controls_Self-Regulating, Parallel-Resistance Heating Cables | Yes | 260524 | 2.2 |  | Product Data
Radiant Heating Electric Cables And Controls_Mechanical Thermostat – Ambient Sensing | Yes | 260524 | 2.3 |  | Product Data
Radiant Heating Electric Cables And Controls_Mechanical Thermostat – Line Sensing | Yes | 260524 | 2.3 |  | Product Data
Radiant Heating Electric Cables And Controls_Electronic Thermostat | Yes | 260524 | 2.3 |  | Product Data
Radiant Heating Electric Cables And Controls_Multi-Point Heat Trace Control Panel | Yes | 260524 | 2.3 |  | Product Data
Radiant Heating Electric Cables And Controls_Cable Installation Accessories | Yes | 260524 | 2.4 |  | Product Data
Raceways_Rigid Metal Conduit - Steel | Yes | 260533 | 2.1 |  | Product Data
Raceways_Rigid Metal Conduit – 316L Stainless Steel Rigid Conduit | Yes | 260533 | 2.1 |  | Product Data
Raceways_Electrical Metallic Tubing | Yes | 260533 | 2.1 |  | Product Data
Raceways_PVC Coated Rigid Metal Conduit – Steel | Yes | 260533 | 2.1 |  | Product Data
Raceways_PVC Externally-Coated Electrical Metallic Tubing And Fitting | Yes | 260533 | 2.1 |  | Product Data
Raceways_Flexible Metal Conduit (FMC) – Galvanized, Zinc Coated, Steel | Yes | 260533 | 2.1 |  | Product Data
Raceways_Liquid-Tight Flexible Metal Conduit (LFMC) | Yes | 260533 | 2.1 |  | Product Data
Raceways_Fittings For Metal Conduit | Yes | 260533 | 2.2 |  | Product Data
Raceways_Conduit Fittings For Hazardous (Classified) Locations | Yes | 260533 | 2.2 |  | Product Data
Raceways_Electrical Metallic Tubing Fittings | Yes | 260533 | 2.2 |  | Product Data
Raceways_Liquid-Tight Flexible Metal Conduit (LFMC) Fittings | Yes | 260533 | 2.2 |  | Product Data
Raceways_Expansion Fittings | Yes | 260533 | 2.2 |  | Product Data
Raceways_Electrical Nonmetallic Tubing | Yes | 260533 | 2.3 |  | Product Data
Raceways_Rigid Polyvinyl Chloride Conduit – Schedule 40 Or 80 PVC | Yes | 260533 | 2.3 |  | Product Data
Raceways_Underground PVC And Abs Plastic Utilities Duct | Yes | 260533 | 2.3 |  | Product Data
Raceways_Liquid-Tight Flexible Nonmetallic Conduit | Yes | 260533 | 2.3 |  | Product Data
Raceways_PVC Conduit And Tubing Fittings | Yes | 260533 | 2.4 |  | Product Data
Raceways_PVC And Abs Plastic Utilities Duct Fittings | Yes | 260533 | 2.4 |  | Product Data
Raceways_Liquid-Tight Flexible Nonmetallic Conduit Fitting | Yes | 260533 | 2.4 |  | Product Data
Raceways_Conduit, Tubing, And Duct Accessorie | Yes | 260533 | 2.4 |  | Product Data
Raceways_Conduit Bodies | Yes | 260533 | 2.5 |  | Product Data
Raceways_Wireways | Yes | 260533 | 2.6 |  | Product Data
Raceways_Surface Metal Raceway | Yes | 260533 | 2.7 |  | Product Data
Raceways_Surface Nonmetallic Raceway | Yes | 260533 | 2.7 |  | Product Data
Electrical Boxes And Fittings_Floor Boxes, Custom Enclosures And Cabinets | Yes | 260534 | 1.4 |  | Shop Drawings
Electrical Boxes And Fittings_Dimensioned Floor Box, And Other In-Slab Box(ES) | Yes | 260534 | 1.4 |  | Record Drawing
Electrical Boxes And Fittings_Dimensioned Handhole, And Other In-Grade Box(ES) | Yes | 260534 | 1.4 |  | Record Drawing
Electrical Boxes And Fittings_ Concrete And Steel Used In Precast Concrete Handholes | Yes | 260534 | 1.4 |  | Certificate
Electrical Boxes And Fittings_Outlet Box Accessories | Yes | 260534 | 2.2 |  | Product Data
Electrical Boxes And Fittings_Clean Room Location Outlet Boxes | Yes | 260534 | 2.2 |  | Product Data
Electrical Boxes And Fittings_Wet Location Outlet Boxes | Yes | 260534 | 2.2 |  | Product Data
Electrical Boxes And Fittings_Nonmetallic Floor Boxes | Yes | 260534 | 2.2 |  | Product Data
Electrical Boxes And Fittings_Device Box Accessories | Yes | 260534 | 2.3 |  | Product Data
Electrical Boxes And Fittings_Junction And Pull Boxes | Yes | 260534 | 2.4 |  | Product Data
Electrical Boxes And Fittings_Floor Boxes | Yes | 260534 | 2.5 |  | Product Data
Electrical Boxes And Fittings_Bushings, Knockouts, Closures And Locknuts | Yes | 260534 | 2.6 |  | Product Data
Electrical Boxes And Fittings_Non-Precast Handholes | Yes | 260534 | 2.7 |  | Product Data
Electrical Boxes And Fittings_Precast Handholes | Yes | 260534 | 2.7 |  | Product Data
Cable Trays For Electrical Systems_Layout Floor Plans And Elevations Showing Cable Tray System | Yes | 260536 | 1.1 |  | Shop Drawings
Cable Trays For Electrical Systems_Certified Copies Of Factory Test Reports | Yes | 260536 | 1.1 |  | Report
Cable Trays For Electrical Systems_Cable Trays, Fittings, And Accessories | Yes | 260536 | 2.3 |  | Product Data
Cable Trays For Electrical Systems_Barrier Strips | Yes | 260536 | 2.5 |  | Product Data
Cable Trays For Electrical Systems_Threaded Hanger Rod | Yes | 260536 | 2.6 |  | Product Data
Cable Trays For Electrical Systems_Preformed Metal Support Channel | Yes | 260536 | 2.6 |  | Product Data
Cable Trays For Electrical Systems_Expansion Anchors | Yes | 260536 | 2.7 |  | Product Data
Cable Trays For Electrical Systems_Toggle Bolts | Yes | 260536 | 2.7 |  | Product Data
Cable Trays For Electrical Systems_Powder-Driven Threaded Studs | Yes | 260536 | 2.7 |  | Product Data
Cable Trays For Electrical Systems_Sleeves | Yes | 260536 | 2.8 |  | Product Data
Cable Trays For Electrical Systems_Sealing Fitting | Yes | 260536 | 2.8 |  | Product Data
Cable Trays For Electrical Systems_Sealing Mortar | Yes | 260536 | 2.8 |  | Product Data
Cable Trays For Electrical Systems_Sealant | Yes | 260536 | 2.8 |  | Product Data
Cable Trays For Electrical Systems_Warning Signs | Yes | 260536 | 2.9 |  | Product Data
Power System Studies_Computer Software Program To Be Used For Studies | Yes | 260573 | 1.5-A |  | Product Data
Power System Studies_Short-Circuit Study Input Data, Including Completed Computer Program Input Data Sheets | Yes | 260573 | 1.5-C |  | Report
Power System Studies_Overcurrent Protective Device Coordination Study Report | Yes | 260573 | 1.5-D |  | Report
Power System Studies_Arc-Flash Study Input Data, Including Completed Computer Program Input Data Sheets | Yes | 260573 | 1.5-E |  | Report
Power System Studies_Study Specialist | Yes | 260573 | 1.5-F |  | Qualifications
Lighting Control Devices_Lighting Control Device | Yes | 260923 | 1.5 |  | Shop Drawings
Lighting Control Devices_Emergency, Operation, And Maintenance Manuals | Yes | 260923 | 1.5 |  | Maintenance Data
Lighting Control Devices_Field Quality-Control Test Reports | Yes | 260923 | 1.5 |  | Report
Lighting Control Devices_Agreement To Maintainenance | Yes | 260923 | 1.5 |  | Report
Lighting Control Devices_Electronic Time Switches | Yes | 260923 | 2.2 |  | Product Data
Lighting Control Devices_Outdoor Photoelectric Switches | Yes | 260923 | 2.3 |  | Product Data
Lighting Control Devices_Daylight-Harvesting Switching Controls | Yes | 260923 | 2.4 |  | Product Data
Lighting Control Devices_Daylight-Harvesting Dimming Controls | Yes | 260923 | 2.5 |  | Product Data
Lighting Control Devices_Indoor Occupancy Sensors | Yes | 260923 | 2.6 |  | Product Data
Lighting Control Devices_Outdoor Motion Sensors | Yes | 260923 | 2.7 |  | Product Data
Lighting Control Devices_Lighting Contactors | Yes | 260923 | 2.8 |  | Product Data
Lighting Control Devices_Emergency Shunt Relay | Yes | 260923 | 2.9 |  | Product Data
Lighting Control System_Lighting Control System | Yes | 260926 | 1.5 |  | Shop Drawings
Lighting Control System_Lighting Controls | Yes | 260926 | 1.5 |  | Record Drawing
Lighting Control System_Software And Firmware Operational Documentation | Yes | 260926 | 1.5 |  | Maintenance Data
Lighting Control System_Lighting Control System | Yes | 260926 | 1.5 |  | Maintenance Data
Lighting Control System_Qualification Data For Testing Agency | Yes | 260926 | 1.5 |  | Qualifications
Lighting Control System_Special Warranty | Yes | 260926 | 1.5 |  | Warranty
Lighting Control System_Distributed Local And Networked Lighting Control Systems | Yes | 260926 | 2.3 |  | Product Data
Lighting Control System_Lighting Control Panelboards | Yes | 260926 | 2.4 |  | Product Data
Lighting Control System_Lighting Relay And Dimming Relay Panels | Yes | 260926 | 2.5 |  | Product Data
Lighting Control System_Low Voltage Control Devices | Yes | 260926 | 2.6 |  | Product Data
Lighting Control System_Load Control Devices | Yes | 260926 | 2.7 |  | Product Data
Lighting Control System_Wall-Box Multi-Scene Dimming Controls | Yes | 260926 | 2.8 |  | Product Data
Lighting Control System_Multi-Preset Modular Dimming Controls | Yes | 260926 | 2.9 |  | Product Data
Lighting Control System_Automatic And Manual Switches And Plates | Yes | 260926 | 2.1 |  | Product Data
Lighting Control System_Field-Mounted Signal Sources | Yes | 260926 | 2.1 |  | Product Data
Lighting Control System_Emergency Power Transfer Relay | Yes | 260926 | 2.9 |  | Product Data
Lighting Control System_Dimmers And Dimmer Module | Yes | 260926 | 2.9 |  | Product Data
Lighting Control System_Infrared Transmitter | Yes | 260926 | 2.9 |  | Product Data
Low Voltage Transformers_Transformer And Related Equipment | Yes | 262200 | 1.5 |  | Shop Drawings
Low Voltage Transformers_Qualified Testing Agency | Yes | 262200 | 1.5 |  | Qualifications
Low Voltage Transformers_Field-Quality Control Reports | Yes | 262200 | 1.5 |  | Report
Low Voltage Transformers_Operation And Maintenance Data | Yes | 262200 | 1.5 |  | Maintenance Data
Low Voltage Transformers_Dry-Type Distribution Transformers (45 KVA Or Less) | Yes | 262200 | 2.2 |  | Product Data
Low Voltage Transformers_Dry-Type Distribution Transformers (Above 45 KVA) | Yes | 262200 | 2.3 |  | Product Data
Low Voltage Transformers_Finishes | Yes | 262200 | 2.4 |  | Product Data
Switchboards_Each Switchboard And Related Equipment | Yes | 262413 | 1.5 |  | Shop Drawings
Switchboards_Qualified Testing Agency | Yes | 262413 | 1.5 |  | Qualifications
Switchboards_Field-Quality Control Reports | Yes | 262413 | 1.5 |  | Report
Switchboards_Switchboard And Components | Yes | 262413 | 1.5 |  | Maintenance Data
Switchboards_Ac Dead-Front Distribution Switchboards | Yes | 262413 | 2.3 |  | Product Data
Switchboards_Bussing And Neutral/Ground Bars | Yes | 262413 | 2.3 |  | Product Data
Switchboards_Lugs & Terminals | Yes | 262413 | 2.3 |  | Product Data
Switchboards_Main Breaker | Yes | 262413 | 2.3 |  | Product Data
Switchboards_Distribution Breakers | Yes | 262413 | 2.3 |  | Product Data
Switchboards_Distribution Fused Switches | Yes | 262413 | 2.3 |  | Product Data
Switchboards_Mimic Bus | Yes | 262413 | 2.3 |  | Product Data
Switchboards_Switchboard Enclosures | Yes | 262413 | 2.4 |  | Product Data
Switchboards_Digital Metering | Yes | 262413 | 2.5 |  | Product Data
Switchboards_Ground-Fault Protectors | Yes | 262413 | 2.6 |  | Product Data
Switchboards_Surge Suppression Devices | Yes | 262413 | 2.7 |  | Product Data
Panelboards_Panelboard And Related Equipment | Yes | 262416 | 1.5 |  | Shop Drawings
Panelboards_Qualified Testing Agency | Yes | 262416 | 1.5 |  | Qualifications
Panelboards_Field-Quality Control Reports | Yes | 262416 | 1.5 |  | Report
Panelboards_Installation In Panelboards | Yes | 262416 | 1.5 |  | Schedule
Panelboards_Panelboards And Components | Yes | 262416 | 1.5 |  | Maintenance Data
Panelboards_Panelboards | Yes | 262416 | 2.2 |  | Product Data
Panelboards_Panelboard Enclosure | Yes | 262416 | 2.3 |  | Product Data
Panelboards_Surge Protection Device | Yes | 262416 | 2.4 |  | Product Data
Panelboards_Digital Metering | Yes | 262416 | 2.5 |  | Product Data
Enclosed Bus Assemblies_Enclosed Bus Assemblies | Yes | 262500 | 1.5 |  | Shop Drawings
Enclosed Bus Assemblies_Testing Agency | Yes | 262500 | 1.5 |  | Qualifications
Enclosed Bus Assemblies_Field Quality-Control Reports | Yes | 262500 | 1.5 |  | Report
Enclosed Bus Assemblies_Enclosed Bus Assemblies | Yes | 262500 | 1.5 |  | Maintenance Data
Enclosed Bus Assemblies_Indoor Plug-In Busway | Yes | 262500 | 2.3 |  | Product Data
Enclosed Bus Assemblies_Plug-In Busway Devices | Yes | 262500 | 2.4 |  | Product Data
Enclosed Bus Assemblies_Plug-In Devices | Yes | 262500 | 2.4 |  | Product Data
Enclosed Bus Assemblies_Fusible Switches | Yes | 262500 | 2.4 |  | Product Data
Wiring Devices_Receptacles | Yes | 262726 | 2.2 |  | Product Data
Wiring Devices_Receptacles, Industrial Heavy-Duty | Yes | 262726 | 2.3 |  | Product Data
Wiring Devices_Ground-Fault Circuit-Interrupter (GFCI) Receptacles | Yes | 262726 | 2.4 |  | Product Data
Wiring Devices_Snap Switches | Yes | 262726 | 2.5 |  | Product Data
Wiring Devices_Dimmer Switches | Yes | 262726 | 2.6 |  | Product Data
Wiring Devices_Led Dimmers | Yes | 262726 | 2.6-1 |  | Product Data
Wiring Devices_Wiring Device Accessories | Yes | 262726 | 2.6-2 |  | Product Data
Wiring Devices_Poke-Thru Assemblies | Yes | 262726 | 2.7 |  | Product Data
Wiring Devices_Prefabricated Multioutlet Assemblies | Yes | 262726 | 2.8 |  | Product Data
Fuses_Certified Test Data Fuse | Yes | 262813 | 1.3 |  | Certificate
Fuses_Qualified Testing Agency | Yes | 262813 | 1.3 |  | Qualifications
Fuses_Field Quality-Control Reports | Yes | 262813 | 1.3 |  | Report
Fuses_Fuses | Yes | 262813 | 1.3 |  | Maintenance Data
Fuses_Class RK1 Fuse | Yes | 262813 | 2.3.1 |  | Product Data
Fuses_Class RK5 Fuse | Yes | 262813 | 2.3.2 |  | Product Data
Fuses_600V 601A-4000A Time-Delay Fuse | Yes | 262813 | 2.4.1 |  | Product Data
Fuses_600V 601A-6000A Fast Acting Fuse | Yes | 262813 | 2.4.2 |  | Product Data
Fuses_600V 601A-6000A Time-Delay Fuse | Yes | 262813 | 2.4.3 |  | Product Data
Fuses_600V Fast Acting Fuse | Yes | 262813 | 2.5.1 |  | Product Data
Fuses_600V Dual-Element Time-Delay Fuse | Yes | 262813 | 2.5.3 |  | Product Data
Fuses_600V Time-Delay Fuse | Yes | 262813 | 2.6.2 |  | Product Data
Fuses_300V Fast Acting Fuse | Yes | 262813 | 2.7.1 |  | Product Data
Fuses_Class T | Yes | 262813 | 2.7.3 |  | Product Data
Fuses_Class S | Yes | 262813 | 2.7.4 |  | Product Data
Enclosed Switches And Circuit Breakers_Enclosed Switches And Circuit Breakers | Yes | 262816 | 1.5 |  | Shop Drawings
Enclosed Switches And Circuit Breakers_Qualified Testing Agency. | Yes | 262816 | 1.5 |  | Qualifications
Enclosed Switches And Circuit Breakers_Field-Quality Control Reports | Yes | 262816 | 1.5 |  | report
Enclosed Switches And Circuit Breakers_Equipment And Components | Yes | 262816 | 1.5 |  | Maintenance Data
Enclosed Switches And Circuit Breakers_ Disconnect Switches | Yes | 262816 | 2.2 |  | Product Data
Enclosed Switches And Circuit Breakers_Bolted Pressure Switches | Yes | 262816 | 2.3 |  | Product Data
Enclosed Switches And Circuit Breakers_Enclosed Circuit Breaker Switches | Yes | 262816 | 2.4 |  | Product Data
Enclosed Switches And Circuit Breakers_Switch Enclosures | Yes | 262816 | 2.5 |  | Product Data
Circuit Breakers_Certified Test Data For Circuit Breaker | Yes | 262818 | 1.4 |  | Certificate
Circuit Breakers_Enclosed Circuit Breakers | Yes | 262818 | 1.4 |  | Shop Drawings
Circuit Breakers_Wiring Diagrams For Power, Signal, And Control Wiring | Yes | 262818 | 1.4 |  | Shop Drawings
Circuit Breakers_Qualified Testing Agency | Yes | 262818 | 1.4 |  | Qualifications
Circuit Breakers_Field Quality-Control Reports | Yes | 262818 | 1.4 |  | Report
Circuit Breakers_Enclosed Circuit Breakers | Yes | 262818 | 1.4 |  | Maintenance Data
Circuit Breakers_Molded Case Circuit Breakers | Yes | 262818 | 2.2 |  | product Data
Circuit Breakers_Thermal Magnetic Circuit Breakers | Yes | 262818 | 2.2 |  | product Data
Circuit Breakers_Adjustable, Instantaneous-Trip Circuit Breakers | Yes | 262818 | 2.2 |  | product Data
Circuit Breakers_Electronic Trip Circuit Breakers | Yes | 262818 | 2.2 |  | product Data
Circuit Breakers_Current-Limiting Circuit Breakers | Yes | 262818 | 2.2 |  | product Data
Circuit Breakers_Integrally Fused Circuit Breakers | Yes | 262818 | 2.2 |  | product Data
Circuit Breakers_Ground-Fault, Circuit Protector (GFP) Circuit Breakers | Yes | 262818 | 2.2 |  | product Data
Circuit Breakers_Lugs | Yes | 262818 | 2.2 |  | product Data
Circuit Breakers_Shunt Trip | Yes | 262818 | 2.2 |  | product Data
Circuit Breakers_Handle Padlocking Device | Yes | 262818 | 2.2 |  | product Data
Circuit Breakers_Insulated Case Circuit Breakers | Yes | 262818 | 2.3 |  | product Data
Enclosed Controllers_Enclosed Controller | Yes | 262913 | 1.4 |  | Shop Drawings
Enclosed Controllers_Enclosed Controllers | Yes | 262913 | 1.4 |  | Maintenance Data
Enclosed Controllers_Load-Current And List Of Settings Of Adjustable Overload Relays | Yes | 262913 | 1.4 |  | Report
Enclosed Controllers_Field-Quality Control Reports | Yes | 262913 | 1.4 |  | Report
Enclosed Controllers_Equipment And Components | Yes | 262913 | 1.4 |  | Maintenance Data
Enclosed Controllers_Control Panels And Relay Panels | Yes | 262913 | 2.2 |  | Product Data
Enclosed Controllers_Motor Starting Manual Switch Controllers | Yes | 262913 | 2.3.1 |  | Product Data
Enclosed Controllers_Fractional Horsepower Manual Controllers | Yes | 262913 | 2.3.2 |  | Product Data
Enclosed Controllers_Integral Horsepower Manual Controllers | Yes | 262913 | 2.3.3 |  | Product Data
Enclosed Controllers_Full-Voltage Controllers | Yes | 262913 | 2.4.1 |  | Product Data
Enclosed Controllers_Combination Controllers | Yes | 262913 | 2.5 |  | Product Data
Enclosed Controllers_Enclosures | Yes | 262913 | 2.6 |  | Product Data
Enclosed Controllers_Accessories | Yes | 262913 | 2.7 |  | Product Data
Variable Frequency Controllers_Variable Frequency Controller | Yes | 262923 | 1.5 |  | Maintenance Data
Variable Frequency Controllers_Field Quality-Control Reports | Yes | 262923 | 1.5 |  | Report
Variable Frequency Controllers_Variable Frequency Controller | Yes | 262923 | 1.5 |  | Shop Drawings
Variable Frequency Controllers_Qualified Testing Agency | Yes | 262923 | 1.5 |  | Qualifications
Variable Frequency Controllers_Variable Frequency Drives | Yes | 262923 | 2.2 |  | Product Data
Variable Frequency Controllers_Line Conditioning And Filtering | Yes | 262923 | 2.3 |  | Product Data
Variable Frequency Controllers_Surge Protection | Yes | 262923 | 2.4 |  | Product Data
Variable Frequency Controllers_Enclosures | Yes | 262923 | 2.5 |  | Product Data
Variable Frequency Controllers_Controls And Communications | Yes | 262923 | 2.6 |  | Product Data
Diesel Engine-Driven Generator Sets_Manufacturer’S Qualifications | Yes | 263213.13 | 1.5 |  | Qualifications
Diesel Engine-Driven Generator Sets_Certification Of Compliance | Yes | 263213.13 | 1.5 |  | Certificate
Diesel Engine-Driven Generator Sets_Maintenance Materials List | Yes | 263213.13 | 1.5 |  | Maintenance Data
Diesel Engine-Driven Generator Sets_Vendor Contract With Equipment Manufacturer | Yes | 263213.13 | 1.5 |  | Report
Diesel Engine-Driven Generator Sets_Schedule | Yes | 263213.13 | 1.5 |  | Schedule
Diesel Engine-Driven Generator Sets_Bill Of Materials For All Equipments And Accessories | Yes | 263213.13 | 1.5 |  | Report
Diesel Engine-Driven Generator Sets_Generator Characteristics | Yes | 263213.13 | 1.5 |  | Report
Diesel Engine-Driven Generator Sets_General Arrangement Drawings | Yes | 263213.13 | 1.5 |  | Shop Drawings
Diesel Engine-Driven Generator Sets_Equipment Shop Drawings | Yes | 263213.13 | 1.5 |  | Shop Drawings
Diesel Engine-Driven Generator Sets_Vibration Isolation Base Details | Yes | 263213.13 | 1.5 |  | Shop Drawings
Diesel Engine-Driven Generator Sets_Alternator Characteristics | Yes | 263213.13 | 1.5 |  | Report
Diesel Engine-Driven Generator Sets_Prototype Torsional Analysis | Yes | 263213.13 | 1.5 |  | Calculations
Diesel Engine-Driven Generator Sets_Battery And Battery Charger Sizing Calculations | Yes | 263213.13 | 1.5 |  | Calculations
Diesel Engine-Driven Generator Sets_Certificate Of Emissions Conformance | Yes | 263213.13 | 1.5 |  | Certificate
Diesel Engine-Driven Generator Sets_Field Test Procedures | Yes | 263213.13 | 1.5 |  | Procedures
Diesel Engine-Driven Generator Sets_Factory Test Procedures | Yes | 263213.13 | 1.5 |  | Procedures
Diesel Engine-Driven Generator Sets_Engine-Generator | Yes | 263213.13 | 1.5 |  | Warranty
Diesel Engine-Driven Generator Sets_Factory Test Report | Yes | 263213.13 | 1.5 |  | Certificate
Diesel Engine-Driven Generator Sets_Certified Field Test Reports | Yes | 263213.13 | 1.5 |  | Report
Diesel Engine-Driven Generator Sets_Stationary Engine-Generator Power System | Yes | 263213.13 | 2.2 |  | Product Data
Diesel Engine-Driven Generator Sets_Outdoor Generator Set Enclosure | Yes | 263213.13 | 2.3 |  | Product Data
Diesel Engine-Driven Generator Sets_Mobile Generator Connection Box | Yes | 263213.13 | 2.4 |  | Product Data
Central Battery Inverters_Each Type And Rating Of Central Battery Equipment Unit | Yes | 263323 | 1.5 |  | Shop Drawings
Central Battery Inverters_Central Battery Systems (Ac Output) | Yes | 263323 | 2.2 |  | Product Data
Central Battery Inverters_Coordination Drawings_Informational | Yes | 263323 | 1.5 |  | Shop Drawings
Central Battery Inverters_Field-Quality Control Reports _Informational | Yes | 263323 | 1.5 |  | Report
Central Battery Inverters_Product Certificates For Central Battery Equipment_Informational | Yes | 263323 | 1.5 |  | Certificate
Central Battery Inverters_Central Battery Inverter And Components _Informational | Yes | 263323 | 1.5 |  | Maintenance Data
Uninterruptable Power Supply_Each Ups And Related Equipment | Yes | 263353 | 1.5 |  | Shop Drawings
Uninterruptable Power Supply_Qualified Testing Agency | Yes | 263353 | 1.5 |  | Qualifications
Uninterruptable Power Supply_Each Product | Yes | 263353 | 1.5 |  | Certificate
Uninterruptable Power Supply_Factory Test Reports | Yes | 263353 | 1.5 |  | Report
Uninterruptable Power Supply_Product Test Reports | Yes | 263353 | 1.5 |  | Report
Uninterruptable Power Supply_Sample Warranties | Yes | 263353 | 1.5 |  | Warranty
Uninterruptable Power Supply_Uninterruptible Power Supply System Equipment | Yes | 263353 | 2.2 |  | Product Data
Uninterruptable Power Supply_Rectifier | Yes | 263353 | 2.4 |  | Product Data
Uninterruptable Power Supply_Inverter | Yes | 263353 | 2.5 |  | Product Data
Uninterruptable Power Supply_Battery System | Yes | 263353 | 2.6 |  | Product Data
Uninterruptable Power Supply_Maintenance Bypass/Isolation Switch | Yes | 263353 | 2.7 |  | Product Data
Uninterruptable Power Supply_Controls And Communications | Yes | 263353 | 2.8 |  | Product Data
Uninterruptable Power Supply_Remote Monitoring | Yes | 263353 | 2.9 |  | Product Data
Transfer Switches_Each Transfer Switch | Yes | 263600 | 1.5 |  | Shop Drawings
Transfer Switches_Qualified Testing Agency | Yes | 263600 | 1.5 |  | Qualifications
Transfer Switches_Field-Quality Control Reports | Yes | 263600 | 1.5 |  | Report
Transfer Switches_Each Type Of Transfer Switch And Components | Yes | 263600 | 1.5 |  | Maintenance Data
Transfer Switches_Automatic Transfer Switches | Yes | 263600 | 2.2 |  | Product Data
Lightning Protection Systems_Lightning Protection System Components | Yes | 264113 | 2.3 |  | Product Data
Lightning Protection Systems_Certified Designer And Installer | Yes | 264113 | 1.3 |  | Qualifications
Lightning Protection Systems_Lightning Protection Systems | Yes | 264113 | 1.3 |  | Shop Drawings
Interior Luminaires_Fixture Assemblies, Nonstandard, Or Custom Lighting Fixtures | Yes | 265113 | 1.4 |  | Shop Drawings
Interior Luminaires_Manufacturer’S Warranty | Yes | 265113 | 1.4 |  | Warranty
Interior Luminaires_Lighting Equipment And Fixtures | Yes | 265113 | 1.4 |  | Maintenance Data
Interior Luminaires_Installation Instructions For Each Fixture Type | Yes | 265113 | 1.4 |  | Procedures
Interior Luminaires_Luminaires | Yes | 265113 | 2.1 |  | Product Data
Interior Luminaires_Lamps | Yes | 265113 | 2.2 |  | Product Data
Interior Luminaires_Led Luminaires | Yes | 265113 | 2.3 |  | Product Data
Interior Luminaires_Lighting Fixture Support Components | Yes | 265113 | 2.4 |  | Product Data
Communications Optical Fiber Backbone Cabling_Communications Optical Fiber | Yes | 271323 | 1.5 |  | Shop Drawings
Communications Optical Fiber Backbone Cabling_Optical Fiber Cable Testing Plan | Yes | 271323 | 1.5 |  | Report
Communications Optical Fiber Backbone Cabling_Rcdd, Installer, Installation Supervisor, And Field Inspector | Yes | 271323 | 1.5 |  | Qualifications
Communications Optical Fiber Backbone Cabling_Plugs Ten Of Each Type | Yes | 271323 | 1.5 |  | Attic Stock
Communications Optical Fiber Backbone Cabling_Jacks Ten Of Each Type | Yes | 271323 | 1.5 |  | Attic Stock
Communications Optical Fiber Backbone Cabling_Patch-Panel Units One Of Each Type | Yes | 271323 | 1.5 |  | Attic Stock
COMmunications Optical Fiber Backbone Cabling_62.5/125-MicrOMeter, Multimode, Optical Fiber Cable (OM1) | Yes | 271323 | 2.3 |  | Product Data
COMmunications Optical Fiber Backbone Cabling_50/125 MicrOMeter, Multimode, Optical Fiber Cable (OM2) | Yes | 271323 | 2.4 |  | Product Data
COMmunications Optical Fiber Backbone Cabling_850 NanOMeter Laser-Optimized, 50/125 MicrOMeter, Multimode Optical Fiber Cable (OM3) | Yes | 271323 | 2.5 |  | Product Data
COMmunications Optical Fiber Backbone Cabling_850 NanOMeter Laser-Optimized, 50/125 MicrOMeter, Multimode Optical Fiber Cable (OM4) | Yes | 271323 | 2.6 |  | Product Data
Communications Optical Fiber Backbone Cabling_9/125 Micrometer Single-Mode, Indoor-Outdoor Optical Fiber Cable (OS1) | Yes | 271323 | 2.7 |  | Product Data
Communications Optical Fiber Backbone Cabling_9/125 Micrometer, Single-Mode, Indoor-Outdoor Optical Fiber Cable (OS2) | Yes | 271323 | 2.8 |  | Product Data
Communications Optical Fiber Backbone Cabling_9/125 Micrometer, Single-Mode, Inside Plant Optical Fiber Cable (OS1) | Yes | 271323 | 2.9 |  | Product Data
Communications Optical Fiber Backbone Cabling_9/125 Micrometer Single-Mode, Inside Plant Optical Fiber Cable (OS2) | Yes | 271323 | 2.1 |  | Product Data
Communications Optical Fiber Backbone Cabling_9/125 Micrometer Single-Mode, Outside Plant Optical Fiber Cable (OS1) | Yes | 271323 | 2.11 |  | Product Data
Communications Optical Fiber Backbone Cabling_9/125 Micrometer Single-Mode, Outside Plant Optical Fiber Cable (OS2) | Yes | 271323 | 2.12 |  | Product Data
Communications Optical Fiber Backbone Cabling_Optical Fiber Cable Hardware | Yes | 271323 | 2.13 |  | Product Data
Communications Optical Fiber Backbone Cabling_Identification Products | Yes | 271323 | 2.14 |  | Product Data
Fire Detection And Alarm Systems_To Support Size Of Standby Batteries | Yes | 283100 | 1.5 |  | Calculations
Fire Detection And Alarm Systems_To Support Voltage Drop For Notification Appliance Circuits | Yes | 283100 | 1.5 |  | Calculations
Fire Detection And Alarm Systems_Qualified Testing Agency | Yes | 283100 | 1.5 |  | Qualifications
Fire Detection And Alarm Systems_Fire Detection And Alarm Systems | Yes | 283100 | 1.5 |  | Shop Drawings
Fire Detection And Alarm Systems_Field-Quality Control Reports | Yes | 283100 | 1.5 |  | Report
Fire Detection And Alarm Systems_Fire Alarm System | Yes | 283100 | 1.5 |  | Maintenance Data
Fire Detection And Alarm Systems_Special Warranty | Yes | 283100 | 1.5 |  | Warranty
Fire Detection And Alarm Systems_Fire Alarm And Detection Systems | Yes | 283100 | 2.2 |  | Product Data
Fire Detection And Alarm Systems_System Wiring And Supervision | Yes | 283100 | 2.3 |  | Product Data
Fire Detection And Alarm Systems_Fire Alarm And Protective System Sequence Of Operation | Yes | 283100 | 2.4 |  | Product Data
Fire Detection And Alarm Systems_Main Fire Alarm Control Unit (FACU) | Yes | 283100 | 2.5 |  | Product Data
Fire Detection And Alarm Systems_Remote Annunciator | Yes | 283100 | 2.6 |  | Product Data
Fire Detection And Alarm Systems_Intelligent System Monitor And Control Devices | Yes | 283100 | 2.7 |  | Product Data
Fire Detection And Alarm Systems_Manual Fire Alarm Boxes | Yes | 283100 | 2.8 |  | Product Data
Fire Detection And Alarm Systems_Smoke Detector | Yes | 283100 | 2.9.1 |  | Product Data
Fire Detection And Alarm Systems_Duct Smoke Detector | Yes | 283100 | 2.9.2 |  | Product Data
Fire Detection And Alarm Systems_Projected Beam Smoke Detector | Yes | 283100 | 2.9.3 |  | Product Data
Fire Detection And Alarm Systems_Carbon Monoxide Detector | Yes | 283100 | 2.9.4 |  | Product Data
Fire Detection And Alarm Systems_Heat Detectors | Yes | 283100 | 2.9.5 |  | Product Data
Fire Detection And Alarm Systems_Notification Appliances | Yes | 283100 | 2.10 |  | Product Data
Fire Detection And Alarm Systems_Magnetic Door Holders | Yes | 283100 | 2.11 |  | Product Data
Fire Detection And Alarm Systems_Fire Alarm Wire And Cable | Yes | 283100 | 2.12 |  | Product Data
Laboratory Airflow Control System_Laboratory Airflow Control System | Yes | 290934 | 2.1 |  | Product Data
Laboratory Airflow Control System_Stash Sensor | Yes | 290934 | 2.1.2 |  | Product Data
Laboratory Airflow Control System_Fume Hood And Local Display | Yes | 290934 | 2.1.3 |  | Product Data
Laboratory Airflow Control System_Airflow Control Device | Yes | 290934 | 2.1.4 |  | Product Data
Laboratory Airflow Control System_Actuation | Yes | 290934 | 2.1.5 |  | Product Data
Laboratory Airflow Control System_Exhaust And Supply Airflow Device Controller | Yes | 290934 | 2.1.6 |  | Product Data
Laboratory Airflow Control System_Fume Hood Control | Yes | 290934 | 2.1.8 |  | Product Data
Filter Housing_Cartridge Filter Housings | Yes | 433113 | 2.2 |  | Product Data
Filter Housing_Surface Finish | Yes | 433113 | 2.3 |  | Product Data
Filter Housing_Housing Accessories - Nameplate | Yes | 433113 | 2.5-1 |  | Product Data

## Type code
Attic Stock
Calculations
Certificate
Color Chart
Leed Requirements
Maintenance Data
Mix Design
Mock-up
MSDS
Pre-Install Meeting Minutes
Procedures
Product Data
Qualifications
Record Drawing
Report
Sample
Schedule
Shop Drawings
Test Data
Warranty